# Erasmus+

THE UNIVERSITY OF THE ARTS LONDON

Erasmus+

British Council, in partnership with Ecorys UK – British Council Cooperation for innovation and the exchange of good practices Strategic Partnerships

Strategic Partnerships for higher education Call 2020

Round 1

Grant Agreement Number 2020-1-UK01-KA203-079249 Report Type Final

Date of submission - Beneficiary Report not yet submitted

James Purnell

Name of legal representative

| Main content: | Report Form |
| --- | --- |
| Number of attachments: | 0 |

# General Information

General information about the project

This report form generated from the Mobility Tool+ consists of the following main sections:

General Information: General information about the project  Inactive Organisations within Project Activities

Context: this section resumes some general information about your project;

Project Summary: this section summarises your project and the organisations involved as partners;

Description of the Project: in this section, you are asked to give information about the objectives and topics addressed by your project;

Project Management

Implementation: this section asks for information about all the stages of the project: implementation of main activities including practical arrangements, participants' profile, impact, dissemination of the results and future plans;

Follow-up

Budget: this section gives a detailed overview of the final amount of the EU grant you request;  Annexes: additional documents that are mandatory for the completion of the report;

For your convenience, some parts of this report are prefilled with information from the Mobility Tool+

# Inactive Organisations within Project Activities

This section doesn't apply for this project

# Context

this section resumes some general information about your project;

| Programme | Erasmus+ |
| --- | --- |
| Key-Action | Cooperation for innovation and the exchange of good practices |
| Action | Strategic Partnerships |
| Action Type | Strategic Partnerships for higher education |
| Main Objective of the project | Innovation |
| Call | 2020 |
| Round | Round 1 |
| Report Type | Final |
| Language used to fill in the form | EN |

## Project Identification

| Grant Agreement Number | 2020-1-UK01-KA203-079249 |
| --- | --- |
| Project Title | Activating Pedagogy for Ceramic Education Futures |
| Project Acronym | CRAFT |
| Project Start Date (dd-mm-yyyy) | 01/09/2020 |
| Project End Date (dd-mm-yyyy) | 31/08/2023 |
| Project Total Duration (months) | 36 |
| Beneficiary Organisation Full Legal Name (Latin characters) | THE UNIVERSITY OF THE ARTS LONDON |

  - National Agency of the Beneficiary Organisation

British Council, in partnership with Ecorys UK – British Council

Identification

For further details about the available Erasmus+ National Agencies, please consult the following page: https://ec.europa.eu/programmes/erasmus-plus/contact_en

# Project Summary

this section summarises your project and the organisations involved as partners;

Please provide short answers to the following questions, summarising the information you have provided in the rest of the report.

Please use full sentences and clear language. The provided summary will be made public by the European Commission and the National Agencies. Background: Why did you apply for this project? What were the needs you have addressed?

Expert Ceramic knowledge is fragmented across Europe, either concentrated in universities, research centres, museums or in areas of specialist industry knowledge such as Delft, Faenza, Stoke-on-Trent, or Selb. Ceramic Education has witnessed a progressive decline within Higher Education due to factors such as cost of provision and declining applications. Moreover, this knowledge is often held by individuals within these institutions and is subject to many external pressures. Higher Education institutions have become the custodians for traditions of skilled artisanship, as the ceramic industry faces a potential decline in skill in the face of economic and technological developments.

Cultural and economic pressures to move towards hybrid practices, combining tacit knowledge of centuries of material expertise with innovations such as additive manufacturing, are pervasive. However, the reality is that the industrial imperative does not align with the sustained heritage of the subject and its pedagogic needs. The educational institution has become the home of the more traditional craft practices and a laboratory for the experimental combination of these traditional technologies with tools and methods of Industry 4.0.

However, this ecosystem is fragile. Ceramics departments across Europe are run by a small, dedicated group of experts, keeping hundreds of years of tradition alive and relying on applicants to find the programmes attractive whilst heritage manufacturing struggles to sustain traditional craftsmanship and relies on cultural tourism as the main income source. This fragility makes the subject particularly vulnerable to outside forces such as recession, the cost of raw materials or more contemporary situations such as

COVID-19, which can impact sales or tourism resulting in a lack of strategy and control and sometimes arbitrary but long-reaching decisions such as discarding intensive craft skills because of costs of production. This scenario is common and can mean the immediate end of a historical process. This problem is mirrored in education where a few cycles of under-recruitment can result in the closure of a department.

Consequently, it is crucial to map this knowledge across Europe, assess the salience of practice to place, build a visual and oral record of specialist processes and techniques, develop methods to effectively share this knowledge across the teaching and expert network and award competency and qualification to ensure heritage crafts skill is relevant to future practice.

This renewed and broad interest in the material should be encouraged, however, there is a need to make access to specialist forms of expert knowledge open and fit for purpose, to record and expose embodied and tacit knowledge, usually gained through experience and repetition, to non-traditional and non-formal learners. A drift towards this more fluid type of learner places the discipline at risk of losing the traditional subject specialist who would dive deep into the intricacies of the subject. This has been compounded by the ubiquitous access to ceramic processes available online on channels such as YouTube and Vimeo, where it is difficult to assess the quality and pedagogical intentions of these sources. Dedicated ceramic teaching platforms such as Ceramic Art Networks Clay Flicks offer higher quality instructable video from experts but there is little evidence of an attempt to decode the tacit knowledge embedded in the expert presentation to the new learner. It is time for a platform or repository which allows an extensive mapping of subject knowledge, a coherent pedagogical approach and a body of teaching tools, projects and instructables that provides a rounded educational possibility. CRAFT has innovatively addressed this problem through its approach to making expertise and knowledge open source, easy to access useful and reconfigurable to need.

CRAFT aimed to support ceramic knowledge retention and transfer by mapping ceramic intangible knowledge (IO1), developing pedagogical approaches and methods based on innovative teaching cards embedding multimedia resources and instructubles (IO2), building an open repertoire of knowledge accessible through an online platform (IO3), and the delivery of three short-term joint staff training workshops for ceramic educators (C1-C3) to train the trainers on innovative methods.

CRAFT draws together the Mapping of knowledge (IO1) and innovative pedagogy teaching cards (IO2) into a knowledge and skills repository ‘Decoding Ceramics’, an online platform (IO3) that packages the information together in an open-access online repository, the first of its kind in the crafts.

Objectives: What did you want to achieve by implementing the project?

CRAFT aimed to support ceramic knowledge retention and transfer by:

- Mapping ceramic places, skills, processes, technologies, intangible knowledge, and training practices for making ceramics (IO1);

- Developing pedagogical approaches and innovative teaching methods to teach ceramics to sustain the future of the subject (IO2);

- Developing skills resources, offering repertoires of knowledge and practice for making ceramics (IO3);

- Developing new training materials and innovative pedagogies to support the training of teachers and practitioners through the delivery of 3 short-term joint staff training workshops for ceramic teachers/trainers/researchers and practitioners (C1-C3).

Project results are going to be disseminated widely as open educational resources, including through the delivery of a final multiplier event (E1) ‘CRAFT: Decoding Ceramics’ held by UAL in London at Central Saint Martins on 15th June 2023 that gathered 50+ attendees across ceramics education from UK, Europe, and China.

Implementation: What activities did you implement?

The project implemented and delivered the following activities:

A virtual Transnational Meeting kicked-off the project aligning partners through a mapping exercise and virtual tour of facilities on 9th and 17th November 2020. During the project, a further 6 in-person Transnational Meetings were organised, rotating the organisation and hosting across the partners. These meetings served to programme, agree on specifications, and review and replan the delivery of the intellectual outputs.

NOVA coordinated the delivery of intellectual Output 1 (IO1) an interactive map visualising the state of ceramics, existing knowledge and where various typologies of skills exist and/or can be acquired, including information on available local materials and historical traditions. The Mapping tool provides the ceramic community with access to fundamental knowledge. It connects expertise, skills, and techniques to regions of intangible cultural heritage, establishing the relationship between tradition and innovation and revealing the movement of ideas, people and skills related to working with ceramics.

Activities implemented:

- Identified and mapped locations, artists, and institutions to be visualised on an interactive map embedded in the IO3 online platform (Decoding Ceramics). The definition of the dataset structure to be used as the content model for the Ceramics dataset.

- Creation of ceramic datasets layered on an Interactive map. Partners contributed to the map providing relevant Points of Interest (POI) featuring locations and artists’ information to be included in the final dataset. The interactive map contains 285 POIs identified, resulting in a task to evaluate available multimedia material produced in each context.

- Deployment and roll-out of the interactive map and content enrichment aggregating new datasets.

KHB coordinated the work leading to the development of the ‘Decoding Cards’ (IO2). Partners compiled a range of teaching approaches from across the partnership that has grown out of a series of prototype cross-partnership teaching workshops. These events shared different teaching practices and curricula via online tools (Miro whiteboards) to map curricula across the network and identify teaching practices collaborative opportunities for shared teaching and introduction of new forms of pedagogy.

Activities implemented:

- Mapping of pedagogical approaches and the curriculum across the partnership, to establish points of intersection for collaborative and challenge-based teaching and to devise a compilation of teaching approaches.

- Creation and testing of 10+ new teaching approaches and tools such as. How to build a community kiln http://decodingceramics.org/card/398

- Adding examples for teaching approaches to a pedagogy-sharing web platform and crosslinking them with the map and the other teaching resources to enable the composition of own new teaching formats.

UAL led the delivery of the Intellectual Output IO3 Decoding Ceramics platform- for sharing discipline knowledge and specialist techniques and skills, across a range of educational settings the platform holds this repertoire for the community, enabling access to knowledge, sharing, and the ability to learn ceramic techniques and skills. The innovative teaching approaches gathered in IO2 will enable the application of the teaching resources from the toolkit across a diverse range of HEI contexts.

Activities implemented:

- Design, development and roll-out of an interactive platform designed to engage with the user and encourage interest and adoption. integrating the different ICT technologies (React for the frontend, Java Spring Boot for the backend, Leaflet for mapping, and d3 for data visualization

- https://craft.arts.ac.uk/ Design and production of dissemination models, resulting in a series of prototype step-by-step teaching modules, case studies, video demonstrations and lesson plans.

- Testing and experimentation of video annotation tools for the design of innovative demonstration videos to devise both the correct methodology and approach on how to annotate gestures and tacit knowledge embodied in different ceramic-making techniques.

The development of the results went through an iterative ideation, design, development, and re-design process. The quality was reviewed by an external Advisory Board. Furthermore, the consortium delivered 3 successful short-term joint staff training workshops (C1-C3) training 38 teachers/trainers. A final Multiplier Event (E1) titled Decoding Ceramics was delivered on June 2023 to present the interactive map (IO1) and the Decoding Teaching Cards (IO2) and engaged 52 external attendees, including 4 international participants.

Results: What concrete outputs and other results did your project produce?

The CRAFT project produced the following concrete outputs and other results:

- A pan-European interactive map of intangible cultural heritage, expert knowledge disappearing skills and techniques (IO1) providing access to 285 ceramics datasets visualised as points of interest and embedded with relevant information on locations, artists information and techniques. This tool represents an innovative solution to

map-based data visualization and user interaction. By considering the map's conceptual purpose and by integrating the different technologies (React for the frontend, Java Spring Boot for the backend, Leaflet for mapping, and d3 for data visualization), we were able to create a dynamic platform that offers a better user experience. What sets this tool apart is its ability to present the sites of interest in a visually engaging and data-rich manner, as well as the ability to connect them, making it a great resource for the ceramic community to explore and understand this data spatially. The underlying content is expected to grow after the project completion through the inclusion of user generated content and point of interest added by stakeholders.

- Decoding cards - an evolving compilation of teaching cards (IO2 Decoding cards) available through the Decoding Ceramics open educational platform (IO3) https://craft.di.fct.unl.p/cards comprising a range of pedagogical and teaching approaches, tools and methods for encouraging participation, uptake, and experimentation in ceramic education. The cards include a series of step-by-step video tutorials, case studies, demonstrations, including a limited series of video tutorials created using an innovative video annotation tool provided by NOVA to shoot demonstration videos that capture through annotations gestures and tacit knowledge and intangible craft skills. craft.di.fct.unl.pt/cards e skills repository hosted on the project YouTube channel.

- Decoding Ceramics - http://decodingceramics.org - an online platform (IO3) serving as repository to provide access to the interactive map (IO1) and to the decoding cards and tutorials (IO2).

- A multilingual glossary of tools to enable effective translation of skills and techniques. Produced in English, German, Portuguese and Czech languages, with the potential to add more. Each tool appears as a photograph with the name in each language alongside, enabling the decoding of the vernacular language that is embedded into craft expertise. https://craft.di.fct.unl.pt/toollist

- A Project website to share the partnership ambition – https://craft.arts.ac.uk/

- Finally, the legacy of the project lies in the building of a new international network of ceramic educators, comprising 5 leading HEI’s and 2 Associated Partners Königliche Porzellan-Manufactur Berlin (KPM) and The Ceramics Research Centre at the University of Westminster (CRC). The network is expected to enlarge further in a near future

bringing together additional expert educators, creative practitioners, curators, designers, manufacturers, and conservators.

Please provide a translation of your project summary in English.

## Summary of participating organisations

| Role of the Organisation | Organisation ID | Name of the Organisation | Country of the Organisation | Type of Organisation | Accreditation of organisation (if applicable) | Partnership Entry Date | Partnership Withdrawal Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiary | E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | Higher education institution (tertiary level) |  | 01/09/2020 | 31/08/2023 |
| Partner | E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | Higher education institution (tertiary level) |  | 01/09/2020 | 31/08/2023 |
| Partner | E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | Higher education institution (tertiary level) |  | 01/09/2020 | 31/08/2023 |
| Partner | E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | Higher education institution (tertiary level) |  | 01/09/2020 | 31/08/2023 |
| Partner | E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | Higher education institution (tertiary level) |  | 01/09/2020 | 31/08/2023 |

5

Total number of participating organisations

  - Associated Partners

In addition to the above formally participating organisations, did you involve associated partners in your project? Yes

Please identify those organisations in the table below:

| Name of the Organisation | Country of the Organisation | City |  |
| --- | --- | --- | --- |
| University of Westminster | United Kingdom | London |  |
| The Königliche Porzellanmanufaktur Berlin | Germany | Berlin |  |

Please explain the involvement of those organisations and how they contributed to the achievement of the project objectives.

The partnership engaged 5 Associate Partners (APs) representing academic, societal and industry stakeholders. The following APs cooperated in the project's implementation.

- University of Westminster (UoW), Ceramics Research Centre (UK) has expertise in ceramics, museology, and collections, and is a leader in the debates surrounding international contemporary ceramic practice. Ceramics in the Expanded Field project delivered the first critical overview of the relationship between contemporary ceramics and curatorial practice in museum culture. The CRC acted as Critical Friends in a series of informal workshops where developments would be presented and discussed.

- The Königliche Porzellanmanufaktur Berlin (KPM) has stood for design "Handmade in Berlin" for over 250 years, with 200+ highly skilled employees. KPM has provided the project with advice and support in technical and design matters, contributing to IO1 development – by providing insights about their craft heritage techniques and skills they work with for the mapping. KPM hosted the C3 event in the factory, a factory tour, space for presentations, and the modelling studio, for a workshop led by (UAL) on decorative stamp making. They granted extensive access to their manufactory and shared strategies, experiences, and learnings about heritage knowledge transfer.

- The British Ceramic Biennale (BCB) (UK), set up in 2008, is the UK’s leading international ceramics festival, located in Stoke-on-Trent. BCB comprises a series of exhibitions for ceramics practitioners; new talent; artists and industry collaborations and a community engagement programme. BCB cooperated with UAL to test the interactive map (IO1), the teaching cards (IO2) and informed the development of the decoding ceramics platform (IO3). BCB promoted the multiplier event (E1) and after the project hosted the symposium titled ‘Decoding Ceramics’ on 11th October 2023 at the Potteries Museum in Stoke on Trent BCB are disseminating the events to their community via their website, newsletters, and social media.

- Royal Delft Group (RDG) (NL) is the only remaining ceramic factory from the 17th century making the world-famous Delft Blue. Royal Delft is an internationally renowned heritage brand employing 55 highly skilled artisans and many international designers making new ranges and giving the heritage collection a new twist. RDG contributed by providing content for IO1 mapping where it is featured as a point of interest, relating to the techniques of hand painting Delftware.

- Kahla Porcelain GMBH (DE), founded in 1844, has a leading reputation for porcelain production, exporting to over 60 countries. Since 1992, KAHLA has hosted the International Porcelain Workshop KAHLA kreativ and in 2010, the Günther Raithel Foundation, which is dedicated to the advancement of education, culture, science, and research related to porcelain. KAHLA contributed to O1 development by sharing knowledge about their production techniques, such as isostatic dust pressing and tutorial videos for the learning resources on the platform.

- Museum of Decorative Arts in Prague (CZ) is a place for innovative learning, facilitating the understanding of the significance of objects of decorative arts and design. The Museum was part of the (C2) event in Prague, allowing trainees to visit the new depository where objects are held and experience a presentation of restoration workshops. The purpose of this event was to deepen the relationship between the museum and educational institutions and to show how craft education can benefit from a close connection with a museum institution. For this reason, because of this event, these workshops now help with teaching technology at UMPRUM. UMPRUM will be exhibiting the results of testing the Storytelling teaching strategy (IO2) at the Moravian gallery in Brno from 17th vember 2023 – 31 August2024 as a part of Made by fire exhibition

https://moravska-galerie.cz/vystavy/pripravovane-vystavy/made-by-fire-4/

- Museu Nacional do Azulejo (PT) is an art museum in Lisbon, Portugal dedicated to the azulejo, traditional tilework of Portugal. Housed in the former Madre de Deus Convent, the museum's collection is one of the largest of ceramics in the world. The Museu was part of TM2, where several traditional and contemporary artistic practices were discussed, and case studies presented to be incorporated in IO1 and IO2.

- Faculdade de Belas Artes Universidade de Lisboa (PT) were responsible for the academic training in ceramic applied to sculpture, painting and design in Lisbon. This institution plays a key role in the dissemination of the project and implementation of the educational cards in Portugal. Several educational aspects were discussed during TM2 and along the project.

UoW and KPM also contributed to the Advisory Board activities.

# Description of the Project

in this section, you are asked to give information about the objectives and topics addressed by your project;

Please provide a summary of your project's concrete results and achievements. Were all original objectives of the project met? Please comment on any objectives initially pursued but not achieved and describe any achievements exceeding the initial expectations.

CRAFT aimed to support ceramic knowledge retention and transfer by:

- Mapping ceramic places, skills, processes, technologies, intangible knowledge, and training practices for making ceramics (IO1);

- Developing pedagogical approaches and innovative teaching methods to teach ceramics to sustain the future of the subject (IO2);

- Developing skills resources, offering repertoires of knowledge and practice for making ceramics (IO3);

- Trialling new training materials & innovative pedagogies to support the training of teachers and practitioners through 3 joint staff training for consortium teachers/trainers/researchers and practitioners (C1-C3).

The project objectives have been met and the partnership has achieved the following concrete results:

- An interactive map providing access to 285+ ceramics datasets (IO1) providing information on ceramic artists or studios, relevant locations, and additional information on the specific techniques that are developed in each place. A User-friendly navigation tool allows the user to dig deep across the map linking via skill, region, materiality etc. The possibilities this approach affords the audience are only now being understood and will require further work to make it effective as a learning tool, that might guide the viewers curiosity through levels of aptitude. The map captures the ceramic intangible cultural heritage, expert knowledge disappearing skills and techniques and connects the points of interest with (IO2) relevant teaching approaches, video tutorials, step-by-step, kit lists and health & safety. The depth of connection from place to teaching approaches makes the platform a powerful teaching and learning tool.

- Decoding Cards (IO2), a compilation of 54 teaching cards proposing: a) Activities for a range of approaches, from basic knowledge acquisition such as how to prepare clay, introduction to glazing, throwing, hand building and extruding, to more advanced cross disciplinary approaches such as CNC milling, of moulds and 3D printing ceramics; b) Lectures; such as what on earth is clay or Glazing using the grid methods, c Projects e.g. building a community kiln, BIG, making large scale sculpture and skilling up, introduction to basic manufacturing techniques, d) Tutorials. Each card contains an introduction, Step-by-Step instructions, a video, information on materials, tools and level of skills needed and time, recommended next steps and further activities. Each card includes as well as health and safety information and linked Point of Interest from the interactive map, showing exemplar places custodian of tradition, techniques or know-how. e cards are a powerful tool which helps to link the mapped expert knowledge to individual learning experiences in acquisition of a large variety of skills and embodied knowledge as well as a contextual framework. The cards are interactive learning resources that are freely accessible through the Decoding Ceramics platform.

- The Decoding Ceramics learning platform (IO3), http://decodingceramics.org that provides access to pedagogy and curriculum mapping tools enabling the sharing of best practices between partners and establishing points of intersection for collaborative teaching approaches. The potential for this approach is now being understood as a truly impactful possibility for aligning curricula across Europe, sharing resources such as demonstrations and lectures, and aligning collaborative teaching opportunities. A series of 40+ prototype step-by-step teaching modules, 60+ video demonstrations and 12 + lesson plans.

- A series of 10+ experimental videos used a novel video annotation tool to design innovative demonstration videos. A result of in-depth work to devise both the correct methodology and approach on how to annotate for the most effective communication of tacit knowledge and craft skills. The Video Annotator tool available through the platform enables users to experiment and prepare their own annotated teaching demonstrations. The new annotated video demonstrations have the potential to push the design of innovative tutorials far beyond the existing ‘showing and talking’ approach that proliferates at present. The development towards video demonstration that embeds other layers of decoded tacit knowledge into the video, using diagrams and technical drawings to explain otherwise hidden details will transform access to specialist knowledge. These videos can be found on the YouTube channel https://www.youtube.com/@DecodingCeramics.

- A Project website to share the partnership ambition and project intentions - www.craft.arts.ac.uk

- The legacy of the project is the establishment of a new network of Higher Education Institutes committed to providing sustainable ceramic education and acting as subject custodians and a home intangible cultural heritage.

In what way was the project innovative and/or complementary to other projects already carried out?

The affordances and limitations that COVID-19 threw up resulted in some unexpected actions that have resulted in innovations. key areas where the project can be considered innovative are:

- The interactive map (IO1) enables the viewer to dig deep into the subject linking via skills, region, materiality etc. Cross-cultural and interdisciplinary connections enable the user to access information beyond the obvious or immediate

to unlock expertise.

- The Decoding Cards (IO2) represent new ways and forms of teaching and dissemination of knowledge towards a more agile and open sharing culture. The teaching cards decode traditional tacit craft knowledge and seek to communicate both traditional and emerging ceramic knowledge to cope with the shift from traditions of subject discipline delivery. For example, the use of motion capture and video annotations are promising tools to make gestures and tacit knowledge explicit to the learners and will transform the way to access and decode specialist craft knowledge. The strong focus on interactive use of the platform (filtering by topic/cross-linking points of interest and techniques/the possibility for the user to generate an individual teaching path) will lead to a long duration of stay on the platform and deep engagement with its content. Users are welcome to contribute to the map and teaching tools after the project’s end and the platform is intended to grow continuously.

- The open educational platform - Decoding Ceramics (IO3) - http://decodingceramics.org - including innovative pedagogy and curriculum mapping encourages the sharing of best practices between partners and establishes points of intersection for collaborative teaching approaches which point to a new distributed open-access form of education.

- Annotated video demonstrations that make tacit knowledge explicit to the learners will transform access to specialist craft knowledge.

While there are several projects being implemented concerning craft mapping and documentation, including videos on traditional techniques, such as Craft Hub which maps studio practices across European craft, the International Academy of Ceramics which maps its membership worldwide, the Museum of Ceramic Art New York has mapped Ceramic World Destinations which presents the subject from a cultural perspective and the Michaelangelo Foundations Homofaber website which provides a directory to find crafts people and artisans the CRAFT project is unique in its focus on the educational and knowledge transfer aspect for the preservation of these skills for present and future generations.

What was the most relevant horizontal or sectoral priority addressed by your project? HORIZONTAL: Social and educational value of European cultural heritage

What were the other relevant horizontal or sectoral priorities addressed by your project? (Multiple selection possible)

HORIZONTAL: Supporting individuals in acquiring and developing basic skills and key competences  HE: Promoting and rewarding excellence in teaching and skills development

In case the above selected priorities are different from the ones in the application, please explain why.

What were the most relevant topics addressed by your project? (Multiple selection possible)  New learning and teaching methods and approaches

International cooperation, international relations, development cooperation

New innovative curricula/educational methods/development of training courses

In case the selected topics are different from the ones in the application, please explain why.

## Participants

Please briefly describe how you selected and involved participants in the different activities of your project.

The primary participants in the activities of the project were research practitioners, educators, and trainers in the field of design and making of ceramics. Teachers and educators were professionals in the areas of ceramics design, conservation and making. Teachers are professors and tutors of the faculty of partner universities who have an interdisciplinary approach to designing and making ceramics to support synergies to promote ceramic skills.

During the development of IO1 Mapping, project partners reached out to 25+ educators, researchers and 25+ master students of Master in Glass and Ceramics Arts and Science and Master in Conservation and Restoration, not only from NOVA but also from the Fine Arts School of the University of Lisbon. Students from the MSc in Computer Science have also been added to the team to contribute to the project to develop postgraduate research work for finalizing their degrees in the context of the project. Furthermore, the association Oficinas do Convento was contact to discuss pertinent information for practitioners and iberian points of interest. The National Tile Museum offered a detailed visit of the museum and collection, giving an opportunity to share the project framework and future impact.

For IO2 KHB contacted Design practitioners working in ceramics and digital technologies. They were invited to give talks and workshops at KHB with design students. The workshops were documented (filmed) and the tutors were

interviewed to derive methods and strategies for IO2. The interviews and documented workshops are shared as video tutorials on the platform. Within the consortium, a first survey was conducted by KHB among the project partners to find out about their general approaches within their departments, the learning goals and skill sets of their students (handcraft, digital tools), and the professional perspectives of their graduates. The second part of the survey asked questions about the department’s resources, structural parameters, and the network the art schools are working within. The survey was then evaluated and flowed into the further development of the IO2 method. A second survey was conducted among the partners to identify overlapping topics within their ceramic education curricula for common learning activities. The main goal was to engage students and teachers from the partner schools for a transnational and active knowledge exchange around a specific topic in the field of ceramics (winter term 2021/22: CRAFT – colours and topography). The experiences evaluated and flowed into the development of the methods for IO2.

For IO3 skills resources platform, the consortium reached out using a letter of invitation to a range of practitioners identified through the IO1 mapping process to record video demonstrations that reflect identified areas of specialist knowledge that are at risk of disappearing or under threat. A similar invitation was made to practitioners, studios, manufacturers, or museums to share any existing video or photographic assets that would complement the development of an open knowledge exchange platform. Participants were selected on what skill sets or knowledge they possessed that the consortium would benefit from capturing, extending through teaching interventions and importantly their openness to sharing.

The secondary participants were reached during the programme development the partners benchmarked their pedagogy across the sector, which was shared among the project partners to inform their methodologies and practice. The engagement with the primary participants is twofold:

- Train the trainer short joint staff training workshops for teachers (C1, C2 and C3): through a process of selection, 3 teachers/educators/trainers from each organisation (34 in total for the 3 events) took part in the workshops to gain knowledge on innovative teaching practices.

- The final multiplier event (E1) ‘Decoding Ceramics’ involved 52+ external attendees reaching out to stakeholders from HEIs, RCA, Westminster College, Morley College, University of Westminster, PXL-MAD (BE) and museums through BCB, NACE, CRAFT Council, the Design Trust, Ceramics Research Centre, Craft Potters Association, London Potters, The Kiln Rooms and other relevant networks.

Also, the project targeted, reached out and influenced secondary participants specifically:

- 20+ teachers/trainers/educators beyond the partner’s organisations requesting capacity-building intervention.

- 18+ people with academic or research interests related to ceramics making and education.

- 50+ organisations informed and briefed for dissemination and networking purposes.

- 18+ ceramic and glass heritage museums, collections, and archives.

- 6+ and HEI associations and umbrella organisations at the EU, national or regional level (e.g., Clay Foundation, ISCAE, IAC, CUMULUS, ELIA).

Participants with fewer opportunities: did your project involve participants facing situations that make their participation more difficult?

No

Approximately, how many persons not receiving a specific grant benefited from or were targeted by the activities organised by the project (e.g. members of the local community, young people, experts, policy makers, and other relevant stakeholders)? Please enter the number of persons here:

750

Please describe briefly how and in which activities these persons were involved.

# Project Management

How did you ensure proper budget control and time management in your project?

The project was awarded a grant of €401,552.00 over a 36-month duration. By the end of the project, the partnership reported actual unit costs totalling € 400,515. The budget was allocated proportionally to work and according to the specialism, capabilities and specific responsibilities and tasks of each partner so that they had adequate resources for the delivery, especially Task Leaders in charge of output production. However, during the project life span, additional resources were needed for the development of intellectual outputs. These were secured operating budget transfers between cost categories and partners reallocating amount not used for Transnational Meetings, LTTs and Multiplier Events.

The Intellectual Outputs production deployed 112% of its budget by mobilising 1521 researchers’ days (1459 days planned). Overall, IO1 and IO3 delivery was more labour intensive than planned. As concern the usage of resources:

- IO1 task was extended, and additional mapping work and information on point of interests were gathered by UAL, UMPRUM and NOVA. NOVA as IO1 Lead reported 164 days out 110 days planned. KHIO reported 44 days out of 75 days budgeted, KHB reported 74 days worked out of 75 budgeted, UAL spent 100 days out of 75 planned and UMPRUM reported 128 days out 75 days budgeted. Extra effort for NOVA, UMPRUM and UAL for additional work were funded through budget transfers using unpent budget from transitional meetings (for example TM1 that occurred virtually), the multiplier events and the resources left unspent by KHIO and KHB from the budget for iO1.

- IO3 leader UAL spent 165 days out a budget of 125 days. NOVA reported 115 days worked out of 85 days planned; KHiO reported 91 days worked days out of 85 planned, while KHB and UMPRUM reported each 85 days worked as per budget. Extra effort for additional work for UAL, NOVA, KHIO was funded through budget transfers at partnership level reallocating between unit costs categories and partners the unspent amount within the unit cost categories of transitional meetings and teachers training activities and multiplier events. And the reallocation of residual budget unspent for IO2 to IO3 especially the work done by NOVA for the platform design, integration, testing and user experience optimisation.

- IO2 Leader KHB spent 129 days out 110 days budgeted, UAL spent 70 days out of 85 planned; NOVA spent 85 days as planned; UMPRUM reported 91 days worked out of 85 days budgeted while KHiO reported 95 days out of a budget of 85 days. Extra effort for KHB, UMPRUM and KHIO was funded through budget transfers at partnership level reallocating between cost categories and partners the amount unspent for unit costs categories like transitional meetings and teachers training activities and multiplier events and the resources underspent by UAL for O2.

The delivery of 6 transnational meetings (TM2-TM7) accounted for 67% of the budget, while the LTTs activities (C1-C3) used up to 78% of the budget. The delivery of the final Multiplier event (E1) used 37% of the budget. Underspending is due to fewer participants attending the TMs, LTTs events and less external attendees for the multiplier events (out 2 events once cancelled). Finally, 97% of the budget allocated to exceptional costs was used to procure materials, consumables and chemicals necessary for the tutorials and teaching and learning activities

For the project management UAL established a Project Management Unit (PMU) to support the coordinator and ensure budget control, financial reporting, and time management. The Project Manager prepared guidelines and templates and organised capacity-building webinars with project partners at the beginning of the project on reporting unit costs and preparing for the audit trail. Each partner appointed a financial officer and kept a record of any expenditure/activity and all proofs of expenditure. The Project Manager required Financial Statements from each partner reporting the actual unit costs incurred every six-months and made suggestions to maximise the grant allocation. This allowed us to monitor resources, identify trends under or over-spending, and plan budget reallocations for emerging needs. The Project Manager shared calendars and sent appropriate reminders to schedule activities and prepared working templates such as a consortium barometer, a self-assessment tool, was used to monitor the partners’ commitment and involvement in the project activities and a Scoping Pro-forma document used to plan IO activities and assignments. A GANTT chart was prepared to schedule the delivery of the project activities and updated throughout the project to prevent time drift delays in activity implementation. Action lists, monthly video catchups and periodic meetings were organized to monitor the project's progress and address its challenges.

Monitoring: How were the progress, quality and achievement of project activities monitored? Please describe the qualitative and quantitative indicators you used. Please give information about the involved staff, as well as the timing and frequency of the monitoring activities.

A set of milestones was defined at the project's beginning for effective, efficient time, quality, and project management. These served as control points to chart progress and critical issues. The CRAFT project benchmarked progress and performance against the following milestones throughout the project lifespan:

- IO1 Desk research (M1-15) - initial findings and field research strategy and action plan were presented at Transnational Meeting 2 in Lisbon in November 2021.

- IO1 Mapping release (M25) - dissemination of mapping data sets were presented at the Transnational Meeting TM4.

- IO2 Pedagogical approaches (M13, M18 and M24) - prototyping, testing and co-authoring teaching methods. Progress was discussed and monitored during the Transnational Meetings TM3, TM4, TM5.

- IO2 Pedagogical approaches and innovative teaching methods (due at M30 and delivered in M34).

- Train the Trainers (delivery of C1-C3 short-term joint staff training workshops delivered in M19, M24 and M29). Feedback gathered and re-engineered to improve the design of the intellectual outputs. Quality and progress monitored during the Transnational Meetings TM3, TM4, TM5 and TM6.

- Multiplier events: the E1 event delivery was postponed to M34, and the second multiplier event (E2) was cancelled. The consortium decided to hold only one final multiplier event instead of two, as they needed more time to complete the delayed release of IO1 and IO2.

The following tools were used by the project coordinator to monitor the project status and progress:

- Financial monitoring: a financial monitoring tool has been prepared by UAL and shared with the financial officers of partners. This tool captures financial data and unit costs accounted for IOs and TMs allowed/allows UAL to track and monitor the overall budget spending. It is used to assess the resources deployed by the partners. The collated data allowed UAL to make suggestions for partners on how to maximize the grant allocation through budget transfers; suggestions were provided at M18, M24 and M30. This tool allows to notice errors and correct them before submitting the Interim Financial Report.

- Risk monitoring: each IO Leader was responsible for continuously identifying and monitoring internal and external risks for the project and informing UAL. Each risk raised by IO Leader was qualified in terms of probability, impact, associated with appropriate mitigation and control actions and was evaluated by the UAL and a course of action was agreed upon. The Project Manager logged and monitored the timely execution of the recovery plan throughout and keep the other partners informed.

- Deviation monitoring: to ensure the monitoring of project deviations from the GA, UAL has created a specific tab in the CRAFT SharePoint named Issues Tracking. This tool allowed the project coordinator together with partners to track the main deviations related to start dates of IOs, postponement of C1, and Partnership Agreement negotiations. Based on these deviations the consortium was able to make changes to the work plan of the project.

- Monthly conference calls: to monitor the progress of the project activities, UAL set-up and chairs monthly conference calls. UAL proposed agendas before the calls allowing partners to contribute to the agendas and add discussion topics based on needs. After the conference calls UAL drafted and shared meeting minutes which were stored on SharePoint.

- The General Assembly (GA): to ensure project governance and monitoring a GA has been set-up including a delegate for each partner. The GA is chaired by UAL and tasked to steer and guide the project implementation. Monthly online meetings were held to monitor the activities and tasks necessary to deliver the IOs.

- Output GANTT: to assure better resource allocation, time management, keep project partners coordinated, see overlapping activities, task dependencies and finish IOs on schedule, UAL created a GANTT which illustrated how the project was implemented and the sequencing of these tasks.

- Quality Assurance Procedures. UAL established a series of Quality Assurance procedures to describe the procedures and log the actions and implemented to ensure the quality of the project deliverables and milestones. The Quality Assurance Manual (QAM) was issued at M3 in line with the ISO–9001 standard.

- Scoping Pro Forma: UAL created and shared with the project partners a Scoping Pro Forma. This document provided the quality guidelines of the Intellectual Output by setting up the intentions, aims, deliverables, defined audiences, academic reference points, team roles and responsibilities, partner’s contributions, and budget of the Intellectual Output. It was completed by IO Leader, shared and agreed with the partners involved in the development of the Intellectual Output.

Evaluation: How did you evaluate to which extent the project reached its results and objectives? What indicators did you use to measure the quality of the project's results?

The CRAFT project progress has been monitored, evaluated, and reviewed by the General Assembly. In terms of the developmental and design future-making aspects of the project, each project partner has shared their progress towards each intellectual output for peer-review assessment and discussion by the General Assembly during each monthly conference meeting.

Concerning the delivery of quality assurance, the coordinator has established a process to ensure a cohesive development of the programme. This process supported the development of a project plan for the implementation used by each project partner. We are using an internal peer review process in which each project partner became a critical observer providing critical insights on the project’s implementation. Toward a comprehensive and holistic representation of overall project quality, the project coordinator together with the General Assembly has assessed various dimensions including goals, content, design and structure, methods and materials used by the partnership during the project’s implementation phase.

We hold sense check sessions at the beginning of monthly conference meetings to discuss openly and collate any matters that a partner wanted to raise or express concerns regarding the implementation of the project. Additional sense-checks between smaller groups of different composition were used in critical phases of the IOs.

An Advisory Board (AB) has been established at the beginning of the project to evaluate the progress of the project, provide critical feedback and quality of the project activities and outcomes. It comprised of 7 external experts:

- Dr Clare Twomey, Professor of Ceramic Art University of Westminster (UK);

- Pia Wirnfeldt, Director of theClay Museum of Ceramic Art (DK);

- Sarah Bräuner, Designer at the Königliche Porzellanmanufaktur Berlin (DE);

- Dr. Filip Suchomel, Orientalist and sinologist specializing in ceramics. Head of Liberec Regional Gallery (CZ);

- Klara Nemeckova, Curator at the Kunstgewerbemuseum Dresden (DE);

- Alexandre Pais, Director, Expert on Tile History Museu do Azulejo (PT);

- Jaume Coll Conesa, director González Martí National Museum of Ceramics and Decorative Arts (ES).

The members were strategically chosen to maximise the project. As senior researchers in key positions in universities around Europe and the world in Design and Ceramic they ensured the resources developed are of high quality. During the project, two AB meetings were organized (September 2021 and May 22) to share their feedback on the project’s implementation. Project Coordinator presented an overview of the project development with partners presenting local approaches and issues arising.

The measures outlined above ought to provide a secure and performable means to monitor, evaluate and critically reflect on the match and realisation between the project aims and objectives and the evaluation of learners and teachers and their perceived future uses of the diverse tools and approaches developed by the project.

For the short-term joint staff training workshops (C1-C3), the workshops were divided in lectures and hands-on

activities by experts in clay, glazes, technical art history, and new technologies. These offered the opportunity to discuss different methodologies to present fundamental knowledge to the students. The success was translated by the implementation of some of these methodologies in the curricula of each partner.

If relevant, please describe any difficulties you have encountered in managing the implementation of the project and how you and your partners handled them. How did you handle project risks (e.g. conflict resolution processes, unforeseen events, etc.)?

The project started in September 2020 during the COVID-19 Pandemic. UAL submitted a request for a delayed project start, this was not granted, and the partnership was instantly plunged into the complexity of a remote implementation. Working in Europe wide lockdowns and travel restrictions made the delivery of the CRAFT project challenging. The Intellectual Outputs structure was designed on the principles of in person participation, access to expertise, capturing and sharing knowledge and the co-design, co-authorship, collaborative experimentation, and development of innovative teaching approaches. It was difficult to activate the project in the spirit of the proposal, A series of mitigations were put in place that delivered the project intentions with revised approaches, including a limited number of fieldwork visits to crafts people's studios were possible to interview and capture skills. Some of this work was implemented later, when restrictions were lifted. Project partners moved to a more distributed model and ‘hacked’ the structure into activities that could be completed locally within the studios of the HEI and managed and shared online to build the project structurally and work towards the more in ‘the field’ live engagement activities.

As a result, we implemented the following mitigations.

- TM1: Project kick-off was conducted by UAL using MS Teams platform – allowing partners to introduce themselves, their capabilities, and their departments virtually. For team building face mapping exercise was conducted to connect participants to tasks. Project Coordinator led the vision back casting exercise where partners were asked about the vision, skills, knowledge, and attitudes for the project.

- Work for IO1, IO2 and IO3 were launched through online workshop using MS Teams and organised by lead partner in charge of the output production.

- Due to COVID-19 field research interviews and filmed demonstrations were delayed and the task duration was extended. IO1 development lasted longer than planned (due date 31 September 2022 – actual delivery 15 June 2023) justify extra time, delay and additional work carried out. Development was longer than planned due to the complexity of the project due to external factors such as Covid impacting on original work plans e.g., could not travel to artist studios. This resulted in significant delays and changes to the workflow as a result partners agreed to extend IO1 to enable completion resulted in a broader remit and greater reach for the desk-based research, which in turn resulted in a more complex version of the interactive map being designed.

- Partners through an online workshop gathered information on curricula, pedagogical approaches and methods for ceramics education used across the partnership. IO2 development started in February 2022 and lasted longer than planned (due date 28 February 2023 – actual delivery 14 June 2023).

- IO3 development started 1 June 2021 and it lasted longer than planned (due 30 June 2023 – actual delivery31 August 2023). The delay was a result of the bourgeoning ambition of the educational platform. In the process of working on the UX and intention to cross link the mapping tool with pedagogical practice, it became apparent how multi layered and content rich the platform needed to be. Consequently, partners were asked to backfill a lot of detail that hadn’t been apparent in the linear development of the project. This was both necessary and beneficial, and added time not anticipated at the start IO3 and elongated the development process of the platform. The team exhausted some time trying to decide and design on the accreditation as detailed in the bid, however this proved intractable to find a one size

fits all accreditation that could be implemented by all partners. Instead, the open access approach to the platform in which users can define competency on entry went someway to superseding accreditation and mitigating this deviation. Project partners are committed to developing an accreditation system going forward and think it would add value to the platform in the future. Additional work and resources assigned to NOVA to design, develop and deploy the IO3 Decoding Ceramics platform and the integration integrating the different ICT technologies into the platform (React for the frontend, Java Spring Boot for the backend, Leaflet for mapping, and d3 for data visualization.

- IO1 and IO3 development has been more labour intensive than planned as additional content and implemented technologies were developed throughout the projects.

- Two multiplier events were planned. However, due to the delays in the development of the intellectual outputs the partners decided to organise a single final event focussing focussing on IO1 and IO2.

- Monthly partnership meetings were held for alignment and discussion.

KHiO and UMPRUM experienced difficulties due to staff changes between September and October 2021 arising from personal and health reasons.

# Implementation

this section asks for information about all the stages of the project: implementation of main activities including practical arrangements, participants' profile, impact, dissemination of the results and future plans;

Please describe the project activities and expenses covered with the Project Management and Implementation grant. If the requested amount is different from the automatically calculated one based on the project duration, please explain why.

The CRAFT partnership carried out the following Project Management and Implementation activities:

- A Partnership Agreement was prepared and shared with project partners which defined the terms that govern the relationships between partners, establishing rights, obligations, and procedures rules for the implementation of the project. The Agreement covers IP, confidentiality, monitoring, and payment arrangements.

- Document Management: UAL set up a SharePoint platform (https://artslondon.sharepoint.com/sites/CRAFT) to store, share relevant project documentation. Each project member was provided with access rights to upload, download, check-in, and check-out content. The platform complies with the General Data Protection Regulation. The platform is used by 22 registered users.

- Distribution of the EU contribution and Financial Management. UAL set-up a specific separate budget code to manage requisitions, procurement and payments operations related to the project implementation. UAL prepared a financial plan for the distribution of the EU contribution to partners. The grant -financing has been promptly transferred to partners in October 2020 and the interim payment in September 2022. During the project, the National Agency paid a prefinancing (€ 160,620.8) and an interim payment (€ 160,620.8) to UAL that re-distributed them promptly to partners in October 2020 and in September 2022.

- The Project Manager and the Financial Coordinator at UAL periodically checked the expenditures targets for the unit costs deployed. Further, UAL created a budget monitoring template and organised a capacity building workshop on how to report unit costs and audit trail for all partners. Each partner appointed a financial officer and kept the record of any expenditure/activity and all proofs of expenditure. UAL delivered four finance workshops/webinars to project partners on how to manage the Erasmus+ unit cost.

- Preparation of the Terms of References, selection, and appointment of the external Advisory Board Members to advise and provide critical feedback on the Intellectual Outputs and provide advice on the project strategic direction. It gathered 7 experts, and a Term of Reference (ToR) was prepared by UAL to explain their role, tasks and including confidentiality arrangements.

- Internal communication channels were established and maintained. A Google group and mailing list (erasmuscraft@googlemail.com) has been created and maintained by UAL to support interactions and communications among the members of the project. The mailing list includes 20 members from partner institutions. Also, UAL set-up a dedicated MS Teams groupware for the monthly conference calls.

- Dissemination and Communication: UAL curated the Plan to define the communication and dissemination activities and channels, target audiences, roles, and responsibilities of partner institutions, as well as information on events organised and attended and papers published in peer-reviewed journals. The partners used Attribution-Non-commercial (CC BY-NC) creative commons licence to release the intellectual output and any dissemination/communication material created during the project.

- Organisation of Transnational Meetings (TM). UAL organised a virtual kick-off meeting on 9 November 2020 during which the meeting partners set the frames for the whole project, revisited project aims, objectives, and agreed on reference points. Following this meeting, 6 in persons Transnational Meetings took place to monitor the progress and status of the project. Project management costs have also been used to cover the costs for the organisation of the TM and to support the preparation of communication and dissemination activities.

- Quality Assurance: UAL prepared and maintained a Quality Assurance Manual (QAM) to define the partners responsibilities, the quality procedures put in place to ensure quality at managerial, scientific, and administrative level.

Please describe the methodology you applied in your project.

The project delivery methodology relied upon critical and creative thinking, participatory methods, problem and challenge-based learning approaches, design for transformational practices and collaborative methods. The project implementation comprised the following interrelated phases that partly overlapped in timing to allow for ongoing review, assessment and fine-tuning of intellectual outputs based on the project’s activities:

Phase 1: mapping. Desk research to identify clusters of excellence and practice within the diversification of production (ateliers, companies). Cultural, historical, and place-making factors were also investigated. A common framework for data harvesting was designed by NOVA, IO1 Leader. Set of criteria to define expertise (technical and tacit knowledge), in order of importance for (future) ceramics: critical, essential, and important. Mapped sector knowledge and reach into Communities of Practices - where is the knowledge/training and facilities. Conducted interviews/videos by all project partners: individual knowledge - go to the experts - where are they? Industry, research centres and individual studios.

Phase 2: pedagogical approaches. Qualitative methodologies were applied, including focus groups, desk, and action

research methodologies. Mapping of pan European teaching methods with an online tool for digital availability (Miro) was initiated by KHB and filled and evaluated qualitatively by project partners. Teaching Methods from other institutions were tested with students within different curricular structures and very varying prior skill sets and resources.

Phase 3: dissemination. This phase is part of the work as a synthesis of local researchers and new didactical approaches. UAL, the IO3 Leader with the support of UMPRUM created a template for video recording, including a description of unifying features such as script, introduction, technique introduction, tools’ introduction, material specification. Development of the Tool library - specification of necessary tools and equipment.

The project management and implementation relied on adaptations of PRINCE2 methodologies. Interactions at the partnership level were driven by a collaborative approach based on consensus, co-creation, and multi-disciplinary collaborations. During the transnational meetings, all partners took major decisions together concerning the project progress, adjustments, task and budget allocation and quality management. Timings for the transnational meetings were re-scheduled along with the development of IOs to allow for review and validation by all partners.

How did the project partners contribute to the project? Please detail specific contributions made by the partner organisations.

All partners worked collaboratively to bring their specific knowledge and expertise across the project. The partners offered broad experience in design education, with a particular emphasis on different areas of ceramic and design studies. The project has been implemented with arrangements made to exploit the complementary expertise of the participating organisations and to create synergies between them. Each of the partners contributed a unique set of skills that provided the project with particularly valuable insights into the evolving ceramic industry.

The project was coordinated by UAL CSM that brought its expertise in heritage manufacturing, specifically in the design and production of tableware and giftware in the volume industry and contributed to the development of Mapping of Ceramic Knowledge (IO1) and the development of Pedagogical approaches and innovative teaching methods for IO2. UAL also led the development of the intellectual output IO3 Decoding Ceramics a Skills Resources repository.

Furthermore, UAL led the project management, financial and contractual responsibilities including the signing of the Grant and Partnership Agreements. UAL chaired the General Assembly where each partner was actively participating, and a Task Leader was identified for each activity based on the experience and capabilities required. UAL organized and chaired three Transnational Meetings (TM1, TM2 and TM7), and the Advisory Board meetings.

NOVA developed and implemented the mapping tool on the map platform, allowing it to be filled by all partners, as part of IO1. NOVA team mapped the relevant places and skills to be included in the map, both in Portugal and Spain. Five videos produced by one of the sites, Oficinas do Convento, in Montemor-o-Novo were selected. In TM2 NOVA promoted dialogue between the partners and other art schools, in particular the Faculty of Fine Arts of the University of Lisbon. IO3 platform design and development and integration of IO1 and IO2.

KHB contributed to the mapping of ceramic knowledge (IO1) actively engaging the regional ceramic industry to identify more potential collaborators for video documentation and interviews and student projects. KHB hosted a virtual workshop on 26th March 2021 where partners gave insights in their art schools and experiences and best-practice examples of student works were shared. KHB was the leader of IO2 Pedagogical approaches and innovative teaching methods. Within this KHB used digital collaborative platforms (Miro and notion) to promote joint cross-university learning among the partners. A topic for the KHB winter term 2021/22 project was chosen, where all the other partners could join in with specialist knowledge from their perspectives and learning goals. KHB developed formats for a growing archive on ceramic student projects (focus glazing). KHB actively contributed to IO3 (filming 12 How-To videos e.g., 3D printing ceramics and CNC-milling of plaster Moulds, interviews with practitioners from design and the industry and documentations of various industrial production techniques). KHB hosted TM6 on 28th March 2023 and the joint staff training workshop (C3) from 29th to 31st March 2023.

For IO1 development, UMPRUM mapped relevant locations in the Czech Republic, Slovakia, Austria, Bulgaria, and Hungary. UMPRUM has been contacting selected factories, artists, and craftsmen to participate in the mapping and share specifications of their knowledge and skills. They have reached more than 30 artists, institutions, and factories. They have proposed drafts scripts for video shooting both technical tutorials and interviews, which other partners commented on. According to them, UMPRUM recorded trial videos, first an expert tutorial on mold making and second an interview with one of the artists who was part of our mapping. They have reviewed the videos together with other partners. For the videos, UMPRUM has created a tool library for plaster workshops. UMPRUM hosted the joint staff training workshop (C2) on 13th-15th September 2022 and the transnational meeting (TM4) on 16th September 2022.

For IO2 UMPRUM tested UAL teaching strategy “Prototyping sprint” and compared them with their teaching methods to articulate the structure of “project card” for “Storytelling” as a teaching strategy.

UMPRUM addressed and further communicated with graphic designer who cooperated with NOVA on development of digital platform and visual of the project. UMPRUM produced 9 videos of technique demonstrations and lectures plus 2 on Kecskemét and Radilina Ceramic.

KHiO worked on IO1 Mapping, inding relevant locations, institutions and artists related to Ceramic Art in the Nordic countries. The institution contacted 20+ artists, educators and researchers working within the field of ceramic art, design, and education. KHiO actively contributed to IO3 producing 22 videos. KHiO also hosted the Transnational Meeting TM5 in January 2023.

How did you communicate and cooperate with your partners? What are the positive and negative elements of the cooperation process? What would you improve if you were to carry out a similar project in the future?

The CRAFT partners communicated and cooperated using the following elements:

- An internal communication and cooperation which relied upon the following tools:

  - Day to day exchange of information by email using mailing lists;

  - The PM prepared and maintained a shared digital schedule and calendar of project activities, deliverable due dates and risk and quality logs. The PM distributed meeting agendas, working papers, minutes, and reports with follow-up actions;

  - A web-based document management platform (CRAFT’s SharePoint) was set up by UAL at the start of the project to facilitate the exchange of information. This platform was provided to each member of the partnership with independent access to working documents, meeting agendas, minutes, supporting materials, and miscellaneous information. To ensure the centralization of knowledge and ease retrieval, this was/is the only store for project related information and is organised with folder structure agreed by the partners.

  - Monthly catch-up calls to keep partners updated and aligned to schedule, to foster cooperation and exchange 40+ catch-up calls organised via MS Teams). Also, further meetings were organised for various task management activities to address specific contingencies such as meeting with the IO Leaders, meeting with PIs.

- 7 Transnational Meetings were organized for cooperation and progress review, including the taking of critical decisions for the project implementation and setting up of working groups for the joint development of the outputs. There interim results were presented. Each meeting is clearly linked to the development and validation of a set of Intellectual Outputs. During these partners made major decisions together on project progress, reviewed experiments, tests and prototypes adjustments, tasks, budget allocation and quality management. Timings for the transnational meetings were aligned with the progress of IOs to allow for review and validation by all partners.

- Reporting Progress. The coordinator issued reporting templates that can easily be consolidated into different reporting formats or intervals. Task Leaders reported to the coordinator on each activity’s progress, identify risk deviations and corrective actions including forward plans. These internal updates formed the basis for the contractual periodic and final report prepared by the coordinator in collaboration with the Task Leaders consolidating the main information.

- A report on the project was published at KERAMICA (https://issuu.com/apicer-ceramicsportugal/docs/keramica369), a publication from the Portuguese industrial association of ceramics. The project was also presented at the XVIIIth Conference of the European Ceramic Society, Lyon, 2nd-6th July 2023.

The partnership is planning to use publications, press releases, social media, videos, and other means of dissemination, including social media. Stakeholders from the ceramic, design educational and innovation and professional communities will be involved from the project outset. Throughout the project, partners are going to collate a list of stakeholders who will form the communications network, creating a mailing list for project communications.

External facing communication channels used by the CRAFT project: the project website, press releases and promotional material.

UAL coordinated, monitored, and managed the internal communication process and tools necessary to encourage the active involvement and participation of all partners. Structured and informal communication processes are both essential for a cohesive partnership and effective delivery of this educational project. The Coordinator and Project Manager were responsible for channelling the relevant information to the partners: communications from the Funding Agency and Advisory Board. For each activity, a working group was established designating for each a partner responsible. The Task Leader prepared action lists allocating responsibilities, scheduling the contributions, and ensuring their

integration.

What target groups were addressed in your activities plan? Were the target groups changed in comparison to the ones identified in the application form?

The CRAFT project created a Dissemination and Communication Plan where partners mapped their intentions and the activities implemented during and after the project to disseminate activities at local, regional, national and the EU level

throughout the existing networks and relations of the partners, and new contacts developed through the project. The CRAFT Communication and Dissemination Plan’s objectives:

- increase awareness of all relevant stakeholders involved:

- communicate, disseminate, promote the take-up and adoption of the projects’ results reach out and briefing the relevant end-users and stakeholders ready for their adoption.

- sensitize and increase awareness on all relevant actors involved.

- devise the most suitable and accessible communication and dissemination channels and tools (website, social media, press releases etc.).

- agree on a dissemination strategy pro-actively supporting the delivery of results through the definition and creation of a visibility package intending to promote and disseminate the project activities and outcomes in the partner countries, all over Europe and at international level (through partners’ websites, informative material, conferences etc.), reaching the target groups.

The target audiences cover the entire ceramic ecosystem from higher education institutions, student and teacher communities to industry associations and organisations at EU, national and regional level. These did not change from the application form and are categorised as:

Primary target audience:

- University academics, trainers and researchers 150 +

- Ceramic Practitionersceramics 150+ Secondary target audience:

- Ceramic manufacturers 10

- Craftspeople and makers 100

- Museum conservators 10

- Technology providers 6

If relevant for your project, did you use or do you plan to use Erasmus+ online platforms (e.g. EPALE, School Education Gateway, eTwinning) for the preparation, implementation and/or follow-up of your project? If yes, please describe how.

As the CRAFT project reached its completion, UAL as coordinator shared the intellectual outputs on the Erasmus+ online platforms. Outputs are released as open educational resources under Creative Commons license. This favours access, use, and reuse by a wider audience. Content generated by the teaching and learning activities allow future engagement with this material by a European-wide specially Design and Ceramic making communities.

## Transnational Project Meetings

This table reflects the information entered in Mobility Tool+. If you would like to change it please do it in the corresponding Mobility Tool+ section. The information presented here will be automatically refreshed after that.

| Meeting ID | 79249-TPM-00001 |
| --- | --- |
| Meeting Title | Transnational Meeting 1 |
| Description of the meeting | The virtual kick-off meeting was held in 2 sessions: the 1st session on 9th November and the 2nd session on 17th November 2020. Welcome by the Coordinator and overview of the project: The Project Coordinator opened the kick-off meeting which was held virtually. Project partners presented each other during the rapid Tour de Table. The presentation was followed by the introduction of the project, its focus, key strengths and vision, and a quick overview of the key Intellectual Outputs. Later, the project GANTT chart was presented indicating the start and end dates for the Intellectual Outputs, dates for the Transnational Meetings and their locations, the Multiplier Events and their locations, and Train the Trainer workshops. Expectations for the project: Partners were asked to share their expectations for this project. IO1 Design Brief: To launch the IO1 Mapping activities: NOVA as Lead of the mapping activities presented the vision and the plan for the output develop scoping the deliverables and the detailed tasks planned for the initial 3 months. This session was structured as an open discussion during which the questions raised were the following: how to ensure that people will be sharing their information. How to set up the mapping approach? How to approach people for the mapping? How will we standardise the information? How will information go to NOVA? What materials does NOVA needs to gather? Which websites to map? IO2 Design Brief: The IO2 Leader KHB presented the IO2 Pedagogical Approaches and Methods and how it can be implemented. KHB presented the aim of the IO2, and the phases of implementation: Preparation, planning, concepts development from Feb until mid Apr 2021; Experimentation + documentation from mid-April 2021 until February 2023; Testing, evolving, and refining in September 2021, February 2020, September 2023 until February 2023; Final documentation from February 2023 until August 2023. KHB allocated partners to their expertise and what they can bring to the project. Partners agreed on engaging with students who can also be involved in IO1 Mapping. Dissemination: visual identity brief, website, social media UAL prepared a |

|  | visual identity brief for the project logo, presentation template and report layout. Partners agreed on UAL approaching Art Temps and commissioning a graphic designer to do the visual identity for the project. Press release: UAL has prepared a press release for the project which will be shared with project partners. The website will be created using WordPress and supervised by UAL. Social media: partners have agreed on having social media accounts. However, they are postponed until the first results are developed. IO3 Design Brief: UAL as Lead presented the Skills Resources by outlining the intention, aims, deliverables, audience, and phases for the platform delivery. The proposed partner contribution was he following NOVA, collaborative design development of open-source knowledge bank/tool kit. The lead KHB development and testing of local level methodologies and tools and transferal of innovative teaching approaches across the network. KHIO, development and testing of local level methodologies and tools and transferal of innovative teaching approaches across the network. UMPRUM, development and testing of local level methodologies and tools and transferal of innovative teaching approaches across the network. Project management: UAL has presented the Coordination Structure of the project and the Quality Assurance Manual. The Project Coordinator led the vision back casting exercise where partners were asked about the vision, skills, knowledge, and attitudes for the project. UAL asked the following: What is the context? What are the skills we want to share? What is the knowledge we want to keep/map/save? What are the attitudes of CRAFT partnership? Later, partners were asked to think of who is the community of the project; who is it for (the project’s vision); who are the experts? Answering these questions, led to the last part of the exercise: what, how, who is doing the outputs of the project: IO1 Mapping, IO2 Pedagogical Methods, IO3 Skills Resources, joint staff training and dissemination. |
| --- | --- |
| Start Date | 09/11/2020 |
| End Date | 09/11/2020 |
| Receiving Organisation | THE UNIVERSITY OF THE ARTS LONDON |
| Receiving Country | United Kingdom |
| Receiving City | LONDON |
| No. of Participants | 16 |

| Meeting ID | 79249-TPM-00002 |
| --- | --- |
| Meeting Title | Transnational Meeting 2 |
| Description of the meeting | The 2nd transnational meeting took place in Lisbon hosted by NOVA on 4-5 November 2021. 13 delegates from the partners attended TM2. The Coordinator, Prof Anthony Quinn, opened Transnational Meeting 2 in Lisbon. Project partners presented each other during the rapid Tour de Table because new joiners from KHiO joined the meeting virtually. The presentation was followed by the Advisory Board Members' presentation. The focus was put on the project outputs by diving deep into each Intellectual Output and presenting the aims and tasks of the outputs. The coordinator also shared the reflections from partners the following: CRAFT launched during the worldwide Pandemic – as a result, there is a mismatch between the proposed work plan written in the bid and our partnership activities. During the meeting the following topics were debated: IO3 Skills Resources. The coordinator presented IO3 and updated on the tasks done such as the prototype videos and the plans for development of the platform. Partners were asked to reflect and share their ambition for this project. The overarching ambition of the project is to create an international open-access digital tool to preserve and share knowledge that otherwise might be lost. Dissemination: The UAL team was working on the development of the website. UAL agreed to host the website on UAL’s domain to ensure the technical maintenance of the website and sustainability post-project Project partners expressed concern that the current logo/visual identity created does not represent the project. Actions agreed: all to agree on the website domain name; all to establish rules and guidelines on the invitation to contribute; UAL to start creating the website in Feb 2022; UAL to redesign the project visual identity alongside the visual graphics of the website. Planning of the C1 short-term joint staff training workshop. UAL as the organiser of Train the Trainers C1 event titled ‘Roadmap for Ceramic Futures: insights and actions from mapping European Ceramic Network - presented the aims and the programme and each partner committed to select 3 researchers/teachers/trainers who will participate in the training workshop in London. IO1 Mapping workshop. NOVA as the leader of presented a preliminary version of the mapping. Partners agreed to contribute to it by providing content and add the legend of the colour coding explaining which colour represents the various categories. Partners agreed to map locations as much as possible at this stage and provide deeper information for 10 places, including the following information/attributes on the place (the best example to follow is Burleigh Factory on the map). Partners agreed on having layers for the map that the NOVA team will create. NOVA was tasked to define the attributes and ask partners to complete a list. This to help the NOVA team to create layers of the map. All partners committed to map as a minimum 10 places each and collecting a rich set of information. THE Burleigh Factory presented on the map is a reference model. The meeting continued with study visit to Trafaria where NOVA is working on regenerating the site into a hub of arts, culture, and creativity education. IO2 Pedagogical Approaches and Methods workshop. The workshop was organised together with staff from the University of Lisbon (Painting |

|  | Department). KHB presented IO2, its objectives and current tasks. To start the knowledge exchange between partners, UAL will organise a session on how to start working with glaze conducted by Duncan from UAL. Partners are encouraged to think about what layer they can add after Duncan’s glaze session. The knowledge exchange aims to show success, failures and to prove that it is a learning process. Actions agreed: KHiO to complete the MIRO board; UAL/Duncan to confirm the date/time for a glaze session. Partners undertake a mapping study visits to the Museu do Azulejo and Conservation Studios and meeting ABM. They also met with the Advisory Board Member Mr Alexandre Silva Pais, Director of the Museu do Azulejo, following a visit to the museum and getting to know the museum's collection. In the wrap-up session the partners confirmed the schedule for the next TM3 meeting and the first joint staff training in London and discussed the opportunity to seek for a project extension through a grant agreement amendment due to COVID-19 impact and start-up delays. |
| --- | --- |
| Start Date | 04/11/2021 |
| End Date | 05/11/2021 |
| Receiving Organisation | UNIVERSIDADE NOVA DE LISBOA |
| Receiving Country | Portugal |
| Receiving City | LISBOA |
| No. of Participants | 13 |

| Meeting ID | 79249-TPM-00003 |
| --- | --- |
| Meeting Title | Transnational Meeting 3 |
| Description of the meeting | The 3rd transnational meeting took place in London hosted by UAL on 25th March 2022. 12 delegates from the partners attended the meeting. The Coordinator, Prof Anthony Quinn, welcomed the participants and presented the agenda and the objectives set for the meeting. The 1st session debriefed and analysed the reflections, feedback and insights from participants who attended C1 short-term staff training on what was well, what did not go well, and what could be improved for the next short-term staff training (C2) in Prague in September 2022 gathered. The critical reflections concerning the short-term joint staff training (C1): ‘it would be great to record the training workshops to preserve knowledge sharing. As we had lots of participants (26 people) it would have been better if two groups were created; it was essential to use to film equipment such as a camera and light. Each partner should contribute to a session within the training event C2 in Prague. It would have been better to have a longer, at least 2-3 hours, reflection session with the participants to gain insights from the participants. As a result, KHB was tasked to carry out a summative evaluation based on the feedback collected from partners and participants. The 2nd session discussed the delivery next steps and partners reviewed the timeline for the upcoming activities and agreed to including the need to seek for a project extension for 3 months until November 2023. UAL to update the project timeline considering the agreed deadlines/times for the activities. The 3rd session was the project website updates and the specifications and use cases for the development of the Decoding Ceramics platform (IO3). The last session discussed the progress of the mapping activities and desk research to make exemplar ceramic making techniques and know-how custodians (IO1). NOVA presented a brief update concerning the data collection phase and the engagement of external stakeholders. |
| Start Date | 25/03/2022 |
| End Date | 25/03/2022 |
| Receiving Organisation | THE UNIVERSITY OF THE ARTS LONDON |
| Receiving Country | United Kingdom |
| Receiving City | LONDON |
| No. of Participants | 12 |

| Meeting ID | 79249-TPM-00004 |
| --- | --- |
| Meeting Title | Transnational Meeting 4 |
|  | The 4th transnational meeting took place in Prague hosted by UMPRUM in Prague (CZ) on 16th September 2022. The TM4 was attended by 10 partners’ delegates. The Coordinator opened the meeting by welcoming the participants and setting the objectives setting for the meeting focusing on the most critical points, such as the IO1 Mapping discussion, a showcase of videos for IO3, IO2 principles of the pedagogy, timeline of the project, agree on dates for TM5 Oslo and the final short-term joint staff training (C3) to be held in Berlin. Then a reflective session was held to debrief and elicit preliminary feedback from the delivery of the short-term joint staff training (C2). The first session focused on progressing and reviewing the work for IO1 Mapping. The session was led by |

| Description of the meeting | NOVA who presented a preliminary version of the map. Partners agreed on the following actions: to name the map as 'Decoding Ceramics' (the partners felt CRAFT was too generic, lacking discipline connection); for NOVA and UAL to work on the graphics and ensure that the project website and the map have the same graphic style, such as logo, font, shift size; for NOVA and UAL to work on developing a map platform with the web developer; for NOVA to remove some of the worlds on the map and leave only: the profile, process/teaching techniques, go-deeper and links; for all to continue updating the map; for NOVA to implement the changes on the map so that KHiO can send the map to people/companies to complete the map themselves. The 2nd session was dedicated to demonstrating the videos tutorials and the initial teaching cards and learning resources produced including the mould making and throwing tutorial from UMPRUM and a video from KPM which was made by KHB, resulting in an analysis of technicalities of video production such as length of video, minimal amount of information, what can be augmented and what should be retained for IO2 In this session led by KHB, partners reviewed IO2 progress and the next steps for the delivery. Principles of Pedagogy were presented. IO2 should represent cross-university knowledge exchange and mediate ceramic knowledge from basic to expert levels. IO2 is for teachers, makers, and students. KHB presented references from other craft related platform such as the Sitterwekr katalog, Critical media lab, Bugh labs - Halle and Material-Archives. Based on this KHB presented the "project cook book" in which all the partners participated. Outcome was a design discussion of a teaching card, with IDEO method cards used as an exemplar for the development of IO2. Further, the partners discussed the course's timespan, participants' skills, available resources, desired learnings, outcomes, and topic/content for the training tutorials. It was agreed to have interlaced learning resources. The meeting concluded by an outlook of the timeline and reminding the upcoming delivery due dates. The coordinator informed the partners that the funder had rejected the project’s extension request for three additional months. The project will officially end on 31st August 2023, as per grant agreement. |
| --- | --- |
| Start Date | 16/09/2022 |
| End Date | 16/09/2022 |
| Receiving Organisation | Vysoka skola umeleckoprumyslova v Praze |
| Receiving Country | Czech Republic |
| Receiving City | Praha |
| No. of Participants | 10 |

| Meeting ID | 79249-TPM-00005 |
| --- | --- |
| Meeting Title | Transnational Meeting 5 |
| Description of the meeting | The 5th transnational meeting took place in Oslo hosted by KHiO on 26th-27th January 2023. The meeting was attended by 11 delegates. Day 1 Participants agreed to reorganize activities into 2 Working-Groups (WGs): IO2 WG Pedagogical Approaches & Methods: partners reviewed what content partners have produced and what content we need to develop in the coming months. The consortium is creating 3 types of educational videos for the teaching cards: 1) Interviews, 2) Skills & 3) Tutorials with step-by-step instructions. Partners agreed on parameters, categories, content management and a timetable for content production. Due to workloads, capacity, quality, language, and video-editing constraints. partners prioritised the content listed. IO3 WG participants co-designed for the Skills Resources: 1) a user journey mapping how teachers and learners will interact with the platform, 2) the layout of teaching cards reasoning on their structure and categories and 3) how to browse through the platform using tags/categories. 4) Mock-ups have been prototyped and each partner agreed to produce the cards to be digitised by NOVA. During the networking session, partners met with Prof Berg (Oslo Metropolitan) who presented the Craft-Hub project (Creative Europe) their online material library. UAL presented CRAFT and highlighted some funding topics for further joint work, spanning from Horizon Europe Cluster 2 and MSCA Staff Exchanges to anticipations on the EIT KIC CCI, the JPI-Cultural Heritage and HERA calls. Discussions continued through a tour of KHIO ceramic facilities and their large-scale kilns. Day 2 The coordinator chaired a reflective session summarizing the work done and soliciting participants' feedback. Concerning IO3, partners co-designed the platform user journey and content considering parameters like topics, time (how long you got), resources and outcomes. UMPRUM designed a mock-up to curate digital teaching cards. Cards will have an introduction, a brief, resources to check out for inspiration and literature reference, information on the experience level, tools and equipment needed, material knowledge and recommended next steps. The cards will form an index of pedagogical tasks. Therefore, a summary of the teaching process plus a multilingual and image-based glossary for tools and equipment were agreed also upon. UMPRUM drafted a glossary and Partners will translate the terms into their language and add pictures. Partners also agreed to 1) Add to cards health & safety info and link to manufacturers’ material data sheets for hazards related to harmful materials/compounds in historical recipes. 2) Use texts, videos, and images created by Partners to illustrate the cards. 3) Produce each card by 7th February 2023. 4) Task NOVA to design an interface to display online the cards on the platform. KHIO reported on the outcomes of WG2 and prompted partners to define the minimum number of videos to shoot and the due dates. The partners also acknowledged the necessity to shoot some videos using NOVA |

|  | motion capture/video annotation technology to decode ceramic gestures, making such intangible know-how more accessible and reproducible. Annotation experiments will start in two weeks, using a KHB video and the NOVA tool to generate the annotations. A further batch is planned for early March 2023, during and after the short-term joint staff training in Berlin. UAL reminded partners to use Creative Commons Share-Alike attribution to comply with the Erasmus+ requirement and include a disclaimer, the project logo, the funder acknowledgement, and the logo. Concerning the platform (IO3) and map development (IO1), NOVA reported on the ongoing development and the next steps. Then NOVA performed a demo to show how to browse and filter points of interest using keywords and what information is displayed. Currently, NOVA is undertaking a quality check to verify the integrity of the datasets migrated on the new map. KHB presented the programme for the Short-Term Joint Staff Training (C3) in Berlin. Participants discussed the activities contributions and reviewed the budget, 10 trainees and not 12 will attend the training, as KHIO will send fewer trainees. The meeting terminated reviewing the dissemination and communication activities. UAL reminded delegates that the Multiplier Event to present IO1 and IO2 is planned on 15th June 2023. KIO informed that in January 2023 they presented the CRAFT during the KHIO research days, while NOVA planned a session at the Fine Art School in Lisbon. NOVA and UAL are also planning to submit a paper to ECERS - Conference of the European Ceramic Society (Lyon 2-6th July 2023) and to prepare an article for Ceramic Review. After the project, to spread the project, UAL will run a symposium at the British Ceramics Biennale in Stoke-on-Trent. |
| --- | --- |
| Start Date | 26/01/2023 |
| End Date | 27/01/2023 |
| Receiving Organisation | KUNSTHOGSKOLEN I OSLO KHIO |
| Receiving Country | Norway |
| Receiving City | OSLO |
| No. of Participants | 15 |

| Meeting ID | 79249-TPM-00006 |
| --- | --- |
| Meeting Title | Transnational Meeting 6 |
| Description of the meeting | The 6th transnational meeting took place in Berlin hosted by KHB on 28th March 2023. 15 delegates attended TM6. The project coordinator opened the meeting, then a brief history of the host institution and tour of the building was given. An update on the financial summary reporting for all partners was presented, including what is still to be spent. The importance of updating hours spent on the project, spending the allocated budget, and producing supporting documentation was stressed. This was to ensure that all funds are spent by the end of the project on 31st August 2023. The group discussed updates on the map (IO1) and films (IO3). The design for Decoding Ceramics will remain the same. There are videos in various stages of production. There was a discussion about partners needing to offer each other extra help and support with the production, including editing and voiceovers. Further technical development discussions were held on several details such as opening a YouTube channel to act as a repository for video demonstrations and instructibles for IO3. UAL has reached out to craftspeople and manufacturers in the UK who have video assets that they are happy to share on the platform. The platform designer from UMPRUM has specified a particular font and supplied a download link for the font. KHiO presented work they had undertaken to look at the categories for films, Pedagogical research and the different methods of teaching. They explained how collaborative working does not always fit into the categories and skills. A proposal was made to add more categories to disambiguate the complexity of searching the map. The coordinator put to the group questions that need to be clarified, including the main device for filming, portraits, and interviews. Partners need to decide a definitive structure of the video tutorials. • Where on the platform do films go when planning the layout? • Where do things fit in before complete design? • Where does it fit as it is all knowledge? There were updates presented on the platform and method cards. NOVA demonstrated the Decoding Ceramics platform (IO3), there has been some challenges and different positions with time and materials. Partners informed that each tab opens and the functionality of the different parts, including the educational cards. Discussions about the title of the educational cards, this will be tested on students to check what best to call it. Summary of what agreed include, Cards and maps are separate and can be linked; maps can be orientated; cards should have a reference to the map; description of what it is, and the page is almost ready with key words. There needs to be a timeline to the publication of the websites and a summary of the educational cards with a back-end descriptor. The last part of the meeting was dedicated to the preparation for the workshops and ensuring that the rooms and equipment were suitable for the training and presentations. |
| Start Date | 28/03/2023 |
| End Date | 28/03/2023 |
| Receiving Organisation | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG |
| Receiving Country | Germany |

| Receiving City | BERLIN |
| --- | --- |
| No. of Participants | 15 |

| Meeting ID | 79249-TPM-00007 |
| --- | --- |
| Meeting Title | Transnational Meeting 7 |
| Description of the meeting | The 7th transnational meeting took place in London hosted by UAL on 15th-16th June 2023 14 delegates from the partners attended the final meeting. Day 1 The project coordinator welcomed the team and introduced the agenda for the meeting. Discussions were held between partners about the timeline for IO3 completion and responsibilities for the remainder of the project. Progress of the Intellectual Outputs were summarised. IO1 Mapping - NOVA has completed the programming and webform. The map is complete. Minor edits needed for Points of Interest, and keywords. It was highlighted that there needs to be a reason for things to be on the map and authors should check details on POI’s. Discussion about how to integrate the completed IO2 teaching formats into the Decoding Ceramics platform (IO3). Updates received about the fundamental aspects including the testing with editing, the resolution of the glossary. UX design issues including the reduction of steps for each task, the order to watch the videos to accompany the tasks or to follow the steps first, it was agreed that it was better for the videos to be placed higher on the page, and all to be kept on one page. The group reviewed the terminology used for tools and it was agreed that this would not change much. IO3 Decoding Ceramics Platform UAL committed to rewrite the introduction text for the project. Communication for the project and photos are to be shared by the group in the SharePoint folder. Updates to the UX of the website were made during the meeting including the sections about the project, how to use the educational cards, Home/About/Team/How to use. Orientation from computer to phone was fixed. The annotator has been tested and it is not sensitive enough. NOVA to continue to debug. A short sense check workshop was conducted by NOVA to explore if nomenclature of platform sections was correct for clarity of user experience. This cantered on checking what was the best title for the pedagogical approaches and innovative teaching methods created in IO2. This was changed on the website live and demonstrated to the group. Final platform design was agreed including size of text, colour, and definitions. Fundamental principles cannot change for different areas, text will be integrated with the products. Co-ordinator introduced the Decoding Ceramics Network Symposium in October 2023 at the Potteries Museum. This will contribute to the dissemination of the CRAFT project. The remainder of the first day of the meeting dedicated to the preparation for the evening’s multiplier event. Day 2 NOVA have published the interactive map online this will be updated and migrated when the transfer to server has been actioned. Miro whiteboard which has been the shared design space for IO3 development, will be updated to reflect that the project is ending. NOVA highlighted that the cycles of the titles and the address of the titles need to be cleaned and this will work for the map. Clarification required for the permissions for the maps if these are to be removed and reinstated. UMPRUM, KHB, and NOVA reiterated that only useful things are to be included and to use links. NOVA will use information from websites to update details and there is no need to seek permission when using public information. Maps were highlighted looking at the similarities, as there are over 300 words for key words. KHB will review the educational cards and keywords by the end of June 2023. POI can be found by alphabetical order. KHB students will be beta testing the platform. The main areas will be: Learn and Decode; Discover; and Decoding Cards. The menu will be updated to display shorter words. KHB will update the size of the menu so this can be shortened. Redesign the cards on Miro include Step-by-step instructions that are to be reduced from 16 to 10 steps. There are many videos and demonstrations. There will be a section for Meet Team and photos of each team are needed to put on the CRAFT website. NOVA will continue with the development of the platform and other issues and updates. Partners agreed to build a There will be curation team for the future sustainability of the project and to review submissions for new people. The project coordinator discussed the Decoding Ceramics network and the five centres of excellence and that to be able to join the network will be on the map. There are terms of engagement to join. The meeting closed by summarising the details of the two days and the availability of partners over the summer with what still needs to be completed before the project closes. |
| Start Date | 15/06/2023 |
| End Date | 16/06/2023 |
| Receiving Organisation | THE UNIVERSITY OF THE ARTS LONDON |
| Receiving Country | United Kingdom |
| Receiving City | LONDON |
| No. of Participants | 14 |

| Total Number of Participants | 95 |
| --- | --- |

## Intellectual Outputs

This table reflects the information entered in Mobility Tool+. If you would like to change it please do it in the corresponding Mobility Tool+ section. The information presented here will be automatically refreshed after that.

| Output Identification | O1 |
| --- | --- |
| Output title | European Ceramic Knowledge: mapping skills, knowledge and expertise |
| Output Type | Studies / analysis – Mapping, scientific literature review |
| Description of the intellectual output | FOCUS: IO1 aimed to map processes, technologies, material knowledge, skills, techniques and recipes for ceramic making, identifying specific places and expertise at EU level. INTRODUCTION: NOVA is the leader of intellectual output IO1. The aim was to develop a map where various typologies of skills are identified, followed by places where those skills exist and/or can be acquired, relations with the available materials and historical local traditions, and finally those we can share and teach. OUTPUT Description: Partners mapped the current state of ceramics training to gather the existing fragmented knowledge in the sector. This output is an innovative teaching training resource for arts and craft education, focused on developing innovative ways to transfer traditional skills and developing a solid repository of ceramic practices. The map is built on a platform developed using JavaScript's library React (version 18.0.0) for the frontend, and Java Spring Boot (version 2.7.0) for the backend. React was chosen for its component-based architecture, which facilitated the creation of a dynamic user interface, while Spring Boot provided a robust and scalable backend infrastructure. For the map visualization, we utilized the Leaflet library (version 1.7.1), a widely adopted mapping library known for its ease of use and versatility. Leaflet allowed us to display geographical data with interactive features seamlessly. To visualize and represent the sites of interest on the map, we employed JavaScript's d3 library (version 7.4.4). D3 (Data-Driven Documents) enabled us to create rich and dynamic visualizations, enhancing the user experience and providing valuable insights. These technologies were seamlessly integrated to provide a comprehensive mapping solution for our project. TARGET GROUP: Ceramic Teachers, Trainers, Educators and interested students/learners. INNOVATION An online interactive resource that provides a directory of craftspeople, production centres, residency and research, heritage and conservation practices, and educational practices. The innovation lies in the distributed nature of the knowledge, dispersing specialism beyond its region of origin and allowing the community to seek expertise, how to resources and workshop teaching aids. EXPECTED IMPACT O1 delivers essential information to artists, craftsmen, designers, industry, conservators, historians, museum curators and material scientists. The knowledge created will also reach the public impacting its preservation, interpretation, and appreciation. TRANSFERABILITY POTENTIAL From the CRAFT mapping a road map of places, experts and available resources and technologies will be available for students, professors, artists, craftsmen and scientists. The proposed methodology is transferable to other sectors like glass, metalwork and silversmithing that share similar cross-cutting needs and challenges for know-how preservation and transfer. DIVISION OF THE WORK: NOVA is the leader of intellectual output IO1. The aim is to develop a map where various typologies of skills are identified, followed by places where those skills exist and/or can be acquired, relations with the available materials and historical local traditions, and finally those we can share and teach. Partners mapped the current state of ceramics training to gather the existing fragmented knowledge in the sector in different regions. All partners contributed to the discussion of the main topics to be included in this form, and to the identification of places of interest. Until now around 285 places have been identified and we are evaluating available multimedia material produced in each place to which we may refer to on the Google interactive map. Each partner is also identifying places and/or skills that are documented by the project, both in academia, craft studios and industry. The production of this material was delayed by the pandemic situation due to COVID-19. NOVA prepared the platform integrating the IO1 map, that also includes a form for the partners to add more sites of interest to it. NOVA also collected 5 videos from the site of Oficinas do Convento, Montemor-o- Novo. UMPRUM produced a set of 5 original tutorial videos for the project. |
| Start Date (dd-mm-yyyy) | 01/09/2020 |
| End Date (dd-mm-yyyy) | 31/05/2023 |
| Available Languages | English |
| Available Medias | Event, Social Media, Oral, Publications, Website, Interactive Resource |
| Leading Organisation | UNIVERSIDADE NOVA DE LISBOA |
| Participating Organisations | KUNSTHOGSKOLEN I OSLO KHIO, THE UNIVERSITY OF THE ARTS LONDON, KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG, Vysoka skola umeleckoprumyslova v Praze |

| Output Identification | O2 |
| --- | --- |
| Output title | Pedagogical approaches and innovative teaching methods |
| Output Type | Methodologies / guidelines – Pedagogical strategy |
| Description of the intellectual output | FOCUS: IO2 aimed to collect, curate, and test a variety of ceramic teaching methods which meet a contemporary teaching and learning practice for a digital educational platform where ceramic heritage knowledge and innovative technological developments in the field are represented. INTRODUCTION: The consortium developed methods for a broad and contemporary ceramic education in HEI, where new requirements for the profession are being reflected and met, such as the preservation of old techniques and the transformation in new contexts, the combination with digital prototyping and production techniques and the increasing evolvement of cross-disciplinary and research-based approaches. OUTPUT Description: The teaching formats were designed to provide a deep knowledge transfer facilitating an agile learning experience and triggering hands-on experimentation for users via a digital medium for global availability. The teaching cards developed include: • interview, tutorial films with annotations to decode hidden/tacit knowledge; • Step-by-step instructions to complement the films; • ‘Shopping lists’ for materials and resources • reference projects (students and professionals); • cross-linking to other teaching formats on the platform to map out a learning path and further suggestions; • connecting the formats with specific skills/topics to POIs on the map. The compilation of formats available on the platform is a showcase of essential ceramic techniques, specialised heritage techniques and places, high-tech and research-based teaching, and best practice work. This gives the user a good sense of the topics, methods and places a contemporary European ceramic education needs to be future-proof and meet HEI standards. TARGET GROUP: Ceramic Teachers, Trainers, Educators and interested students/learners. INNOVATION IO2 bridges the gap between the mapped expert knowledge spread across Europe (IO1) embodied in artists/design studios/manufactories etc. and the individual learning experience by providing insight knowledge about techniques, places, materials, and contextual frameworks within the field. Because of the digital content, heritage knowledge can be preserved live and be passed on within new contexts and learning environments. EXPECTED IMPACT The teaching methods and the implementation in the platform improve access to ceramic education and expert knowledge for teachers, practitioners as well as learners. The cross-linking between old knowledge and new technologies are easier due to the lively presentation of projects and simple teaching tools. In the long-term we expect IO2 and the platform to be a guide throughout studies for learners but also as a database for industries and serve as a “meeting point” for traditional ceramic experts and pioneers in the field. TRANSFERABILITY POTENTIAL The decoding of ceramic knowledge, sharing innovative teaching methods from leading European universities and providing this within an open-access platform has the potential to work as an accelerator for HEI education as well as for collaborations of craftswomen, designers, and artists with industrial partners DIVISION OF THE WORK: The partners illustrated their teaching methodologies with best-practice work by students in their departments (from BA to MA and PhD levels). Projects included artistic work, traditional (manual) techniques, industry collaborations and research-led digital fabrication projects. Each partner participated and emphasized its teaching focus. The approaches and student projects were evaluated by the partners and parameters and topics for the teaching resources were identified. The parameters served as ‘building blocks’ for teaching resources and to ensure high flexibility potential in use for teaching and learning realities: - Timespan of course (hours, days, semester) • Skills of participants (beginner, advanced (BA and MA levels), PhD, professionals) • Resources (hands to ceramics workshop to digital prototyping machinery) • Desired learnings (basic to advanced techniques to broader contexts, such as sustainability, community building) • Desired outcomes (material study, conceptually skilled, prototype, ready for industry) The parameters were crossed with related subjects (classical, new ceramic techniques, product categories (tableware, figurines, tiles, robotics etc.). Everything on the premise that each institution considers its specialisation, curricular structures, prior knowledge, technical skills of the students and the workshop resources. With this a broad spectrum of learning methods were mapped. Cross-referencing between institutions is possible and made the method set even more comprehensive, more accessible and variable for the future target groups. |
| Start Date (dd-mm-yyyy) | 01/02/2021 |
| End Date (dd-mm-yyyy) | 31/05/2023 |
| Available Languages | English |
| Available Medias | Website, Oral, Social Media, Publications |
| Leading Organisation | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG |
| Participating Organisations | THE UNIVERSITY OF THE ARTS LONDON, Vysoka skola umeleckoprumyslova v Praze, UNIVERSIDADE NOVA DE LISBOA, KUNSTHOGSKOLEN I OSLO KHIO |

| Output Identification | O3 |
| --- | --- |
| Output title | Skills resources offering repertoires of knowledge and practice for making ceramics |

| Output Type | Learning / teaching / training material – Toolkit |
| --- | --- |
| Description of the intellectual output | FOCUS: IO3 creates an open, freely accessible repository of discipline knowledge and skill that is for the ceramic community from novice learners to experienced educators. Taking the form of an online platform that contains an interactive Map (IO1) and a range of innovative pedagogical approaches (IO2) with IO3 providing a skills repository and building the infrastructure, workflow, and user interface to make this information accessible and implementable. IO3 provides the wider craft community with an open knowledge resource that provides access to teaching tools for ceramics education. The primary objectives of IO3 are to make knowledge accessible, by decoding tacit knowledge of craftspeople to preserve the highly specialised distributed knowledge in one place for future practitioners and subject sustainability. INTRODUCTION: IO3 addresses the need for educators to have an extensive and effective resource at their disposal that collects diverse knowledge, skills, and expertise in one place that spans the entire possibility of the discipline. IO3 platform is an ambitious solution to this problem, connects learners and educators directly to experts, hard-earned skills, and specialist knowledge. It crosscuts the traditional barriers to knowledge such as access to education or proximity to regional centres of excellence and provides the visitor with the tools to learn skills and to construct these skills together into a more complex process that fulfils the specific needs of the user. This enables the transdisciplinary implementation of innovative teaching approaches, within a range of contexts. OUTPUT DESCRIPTiON: The IO3 skills platform is a dynamic teaching & learning tool that attempts to decode tacit knowledge, collect knowledge, skills, and expertise in one central open resource, that allows for easy adoption and implementation. The IO3 Platform ‘Decoding Ceramics’, is a configurable skills repository of transferable knowledge, comprising instructables, demonstrations and 70+ inspirational videos uploaded onto a dedicated a YouTube Channel. TARGET GROUP: IO3 is aimed at a diverse cross section of the Ceramic Community from those in formal education, novices in home studios, to early career professionals, schoolteachers and FE/HE lecturers and experienced makers. INNOVATION IO3’s innovation lies in the approach to making expertise and knowledge open source, easy to access, useful and reconfigurable to need. Prior to this action, expert knowledge has been hard earned, closely guarded and difficult to access. IO3 pulls together the Map (IO1) and innovative Pedagogy (IO2) and presents a unified platform that packages the information together in a format that transform the acquisition and sharing of knowledge in a Europe wide action that will reinvigorate education, research and heritage industry, acting as a repository for craft techniques and teaching methods to pass on knowledge in a way that is applicable to the learners contexts and needs. EXPECTED IMPACT IO3 transforms a database of complex knowledge and skills into a functional accessible resource that educators and learners can utilize or learn from daily. The connection of an interactive map to pedagogical approaches extends the potential pool of educators and in turn valorises hard to access or at-risk craft skills. In turn it is expected that expertise will be valued through exposure on the platform resulting in an upsurge in requests for experts to teach across the sector. TRANSFERABILITY POTENTIAL This output drives a resurgence of expertise and a transferral of possibility from location specificity of heritage manufacturing towards a discipline and industry that is agile and modern whilst aware of its provenance and craftsmanship. The output has great interdisciplinary transferability potential into other craft disciples such as glass, metal, and textiles. DIVISION OF THE WORK: UAL led on the conceptual development of IO3, with the skills repository and open education Platform. NOVA worked closely with UAL and were instrumental on the development of the UX, integration and programming of the Platform. KHiO KHB & UMPRUM contributed to the development of IO3 with videos demonstrations, instructible’s and development support. |
| Start Date (dd-mm-yyyy) | 01/06/2021 |
| End Date (dd-mm-yyyy) | 31/08/2023 |
| Available Languages | English |
| Available Medias | Press, Website, Video, Publications, Network, Internet, Oral |
| Leading Organisation | THE UNIVERSITY OF THE ARTS LONDON |
| Participating Organisations | KUNSTHOGSKOLEN I OSLO KHIO, UNIVERSIDADE NOVA DE LISBOA, KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG, Vysoka skola umeleckoprumyslova v Praze |

## Multiplier Events

This table reflects the information entered in Mobility Tool+. If you would like to change it please do it in the corresponding Mobility Tool+ section. The information presented here will be automatically refreshed after that.

| Event Identification | E1 |
| --- | --- |
| Event Title | Decoding Ceramics |

| Description of the multiplier event | UAL organised the final multiplier event titled ‘CRAFT: Decoding Ceramics’ to present to the wider ceramic art and design community the intellectual outputs (IO1) the interactive map and IO2 Decoding Cards, a series of pedagogical approaches and innovative teaching methods. The event gathered 52 external participants from across the ceramic discipline, including heads of departments, teachers, graduates, makers, business coaches, as well as 4 international attendees. The event format included a keynote presentation and a series of talks to present the intellectual outputs and to debate their potential impact followed by a wrap-up and Q&A session to engage with audience. Welcome and introduction. The coordinator (UAL) provided a contextual introduction explaining the sense of urgency behind the CRAFT partnership and the drive and imperative for the project to be established, as this expert knowledge is under threat. Universities are the holders of intangible cultural knowledge and act as custodians of the pedagogical needs and the funding of the de facto of the ceramic discipline at large and the ceramics industry. Professor Roger Kneebone keynote speech on the importance of Expertise and the Path to Mastery spoke about the journey to mastery and the idea of becoming an Expert. He introduced the three stages of becoming an expert from Apprentice to Journeyman, and finally Master. The partners presented the outcomes and potential impact of the interactive map (IO1) and of the Decoding Cards and video tutorials (IO2) exemplifying the breadth of practice involved in the development of the IOs. The interactive map (IO1) and the underlying desk research and process of mapping knowledge and expertise across Europe was presented by the NOVA team. Some time was taken to illustrate how the knowledge within the map can be accessed, and how typologies of practice or interrelated skills are connected within the map for a heightened user experience. Annotation and Gesture capture were presented by the computer science team from NOVA, who explained how these tools can be used to unlock tacit Knowledge for the benefit of platform user. The team also illustrated how to use these tools to create user generated augmented video demonstration. Decoding Cards which covered Pedagogical Approaches (IO2) was presented by other partners with the KHiO team showcasing some inspirational videos embedded into the IO2 teaching cards. For example, the Claymates workshop where 15 students and teachers undertook an immersive shared learning experience in nature with the clay material. The pedagogical theories underpinning the workshop were explained including Communities of Practice, Troublesome Knowledge, and Productive Failure. Rethinking Ceramics teaching, presented by UMPRUM, illustrated how their department had led on the adoption of two new pedagogical approaches, that they had experienced during participation in the CRAFT project and its training events. The Sprint Technical Introduction, a teaching method which they mutated and adapted from a teaching UAL and the ‘Storytelling’ teaching module (http://decodingceramics.org/card/411) designed by UMPRUM as articulation of a new teaching strategy developed in IO2 in cooperation with the Museum of applied arts. Participants learn how to connect historical objects with the contemporary ones on the conceptual level. The functionality of Decoding Ceramics teaching cards (IO2) and where users can find them on the Decoding Ceramics platform (IO3) were presented by KHB. It was explained how the materials can be linked to each other, from step-by-step tutorials to semester projects. Examples were presented selected from semester projects at KHB where digital competences of the students were linked to ceramic techniques. A networking event closed the event hosted during the CSM Degree Show Exhibition where they could meet new colleagues within the field, discuss collaborations and see the work of the next generation of graduates. |
| --- | --- |
| Country of Venue | United Kingdom |
| Start Date (dd-mm-yyyy) | 16/06/2023 |
| End Date (dd-mm-yyyy) | 16/06/2023 |
| Intellectual Outputs Covered (using Output Identification number) | O1;O2 |
| Leading Organisation | THE UNIVERSITY OF THE ARTS LONDON |
| Participating Organisations |  |

| Event Identification | E2 |
| --- | --- |
| Event Title | ACTIVATION - Ceramics in the Open Field. Preserving skills through innovative teaching methods |
| Description of the multiplier event | The CRAFT consortium decided to cancel the E2 in Prague for several reasons. The consortium officially requested to extend the project for 3 additional months, which would have allowed UAL and UMPRUM to organise E1 and E2 as part of well-known ceramics events in London and Prague, respectively. As the request for an extension was rejected, it became too challenging for the UMPRUM team to organise a multiplier event. The consortium decided it would be more impactful to move 20% of the overall multiplier budget equaling 3,000 EUR, to NOVA to work on the platform and map development. The budget (3,000 EUR) was instead transferred to the intellectual output to provide 22 researchers days to NOVA to undertake additional IT development work on the platform to debug, redesign and testing it (IO3). |
| Country of Venue | Czech Republic |

| Start Date (dd-mm-yyyy) | 01/09/2020 |
| --- | --- |
| End Date (dd-mm-yyyy) | 30/08/2023 |
| Intellectual Outputs Covered (using Output Identification number) | O3;O2;O1 |
| Leading Organisation | Vysoka skola umeleckoprumyslova v Praze |
| Participating Organisations |  |

## Learning/Teaching/Training Activities

This table reflects the information entered in Mobility Tool+. If you would like to change it please do it in the corresponding Mobility Tool+ section. The information presented here will be automatically refreshed after that.

| Activity No. | C1 |
| --- | --- |
| Field | HE |
| Activity Type | SP-HE-SHORT |
| Description of the activity | The C1 Train the Trainers event was hosted by UAL in the extensive ceramic department studios on 22nd-24th March 2022. Participants brought educators from each of their institutions, where they were introduced to key findings of the CRAFT project and involved in workshops to explore the innovative teaching approaches and methods that can be adopted or tested in their teaching practice. As a result of COVID restrictions, C1 was more holistic in its approach, bringing together a broader presentation of IO1, 2 and 3. Aims of the training: • The training event aimed to exemplify the findings of the craft project so far. • Orientated partners to the insights and findings of the mapping exercise (IO1), presented key aspects of the mapping exercise and drew out examples of important knowledge that should be recorded and shared. • Presented innovative teaching approaches (IO2) through analogous or prototype activities. • Explored and prototyped dissemination approaches (IO3) and gesture capture tools. Participants: • Shared best examples from their specific research through a form of demonstration or action. • received the discipline-specific information and undertook a workshop to explore different modes of teaching and sharing knowledge. • Received tangible tools and principles to enable the adoption of the CRAFT project into day-to-day teaching. Agenda Day 1 – IO1 Overview, Context and Mapping started with a general orientation and overview to kick off a series of teaching experiences. UMPRUM: led the workshop on how to shoot a video with minimal equipment, like a field kit for shooting and postproduction. This involved two technical demonstrations, throwing (how to throw a large-scale object) and wax mold for casting complicated models for figurines. NOVA: An afternoon/day spending on teaching and testing the annotations tool on the already existent films to be made as part of C1 by UMPRUM. This was done in a collaborative session with a projector/screen for the participant to explore what needs to be annotated. The session was extended to live capture with an external webcam. Day 2 - IO2 Presentation, insights and sharing workshop UAL introduced an approach used in the department to activate the city's history as a teaching context. We started in Borough market and looked at Southwark Cathedral’s 17th-century delftware kiln, built into the foundations. In the workshop, the trainees had material samples of London Clays, Sprig moulds, Roulettes, and Terra sigillata for Burnishing. Students use these to create their first project. Ritual, Ceremony and Celebration. The session reflected on how to make context impactful in learning. KHiO: Introduction to how we train students to develop individual glazes. The teacher described how he does this, why he does it like this and how other teachers are doing it. Day 3 IO3 Skills resources A joint ideation session on proposing, gathering, and creating ideas for a lively cross-university and -country knowledge exchange about ceramic education methods. The aims of the session were to: • get an overview of current analogue, digital, and hybrid ceramics education methods • develop joint strategies and methods to generate a lively exchange of knowledge among teachers and students (analogue/digital) The session was divided into several subtopics, such as: • methods for educating advanced tools/technologies. • short exercise on the topic of 3d data x craft. - methods for context + concept in ceramic education. It consisted of an ideation session, a practical exercise, and an overview of KHB teaching methods + best practice student projects. KHiO discussed the impact and complexities of running two large-scale kilns. Knut also shared his experiences with pitfalls, costs, happy accidents, and other issues. In addition, we shared images from our facilities along with the talk. The training finished with a session of Reflections and informing the next steps. This provided a series of prototype tools to be tested in the project's next phase, specifically in the developments of intellectual outputs IO1, IO2 and IO3. Outcomes for the learners • Understood ceramic knowledge networks across Europe. • Had up-to-date perspectives and reflections on the state-of-the-art approaches for dissemination. • Learned from the heritage crafts industry and developed a new skills portfolio. • Devised approaches and action plans for activating the network. Attendance: the training was attended by 2 trainees from UAL, 3 trainees from NOVA, 2 trainees from UMPRUM, 3 trainees from KHB and 1 trainee from KHiO. |

| Country of Venue | United Kingdom |
| --- | --- |
| No. of Participants | 11 |
| Participants with Special Needs (out of total number of Participants) | 0 |
| Accompanying Persons (out of total number of Participants) | 0 |
| Is this a long-term activity? | No |
| Funded Duration (days) | 33 |
| Participating Organisations | THE UNIVERSITY OF THE ARTS LONDON, UNIVERSIDADE NOVA DE LISBOA, Vysoka skola umeleckoprumyslova v Praze, KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG, KUNSTHOGSKOLEN I OSLO KHIO |

| Activity No. | C2 |
| --- | --- |
| Field | HE |
| Activity Type | SP-HE-SHORT |
| Description of the activity | The C2 Train the Trainers event was hosted by UMPRUM in the ceramic department studios on 13th-15th September 2022. Each institution invited educators from their specific departments to introduce them to the strategic findings of the CRAFT project. Participants were involved in presentations and workshops to explore the innovative teaching approaches and methods that can be adopted or tested in their teaching practice. C2 was built on ideas and requirements discovered during previous C1 training. The aim of the training was to test the innovative teaching methods proposed by IO2 and the tools proposed by IO3. Agenda: Day 1 Overview, a lecture led by UMPRUM introducing storytelling as a teaching strategy (IO2), demonstration in the Museum of Applied Arts Depository. Afternoon joined a session by KHB and UMPRUM on different strategies for developing glazes stone glazes. Lecture and practical workshop, followed by a discussion on strategy of sharing the outcomes - glaze library, tool library (IO2, IO3). Day 2 a lecture led by KHiO introducing teaching strategies in guiding the students to develop their artistic expression regarding ceramic surfaces, followed by presenting the tools. (IO2, IO3). Afternoon joined session by KHB and UMPRUM. The KHB team introduced the idea of “method cards” as a tool for designing a didactic structure (IO2, followed by a discussion on how to introduce and implement new technologies in teaching traditional crafts. The rest of the session was dedicated to a workshop with a plaster mill and robotic arm. Day 3, Prototyping sprint led by UAL. Introductory lesson for multiple techniques (IO2). Afternoon session by NOVA workshop on functional and usability evaluation of the Map Interface Platform (IO1). All participants tested the mapping process. This testing provided a set of requirements for further development of the maps. The training finished with a session of reflections and planning the next steps. Outcomes for the learners: • Had knowledge of various teaching strategies and innovative approaches to sharing tangible knowledge. • Had learned new skills from the set of demonstrations. • Understanding the importance of the development of a didactic structure. • Had knowledge on implementation of innovative technologies in dissemination. Attendance: the training was attended by 3 trainees from UAL, 3 trainees from NOVA, 3 trainees from UMPRUM, 3 trainees from KHB and 2 trainees from KHiO. |
| Country of Venue | Czech Republic |
| No. of Participants | 13 |
| Participants with Special Needs (out of total number of Participants) | 0 |
| Accompanying Persons (out of total number of Participants) | 0 |
| Is this a long-term activity? | No |
| Funded Duration (days) | 39 |
| Participating Organisations | THE UNIVERSITY OF THE ARTS LONDON, KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG, KUNSTHOGSKOLEN I OSLO KHIO, UNIVERSIDADE NOVA DE LISBOA, Vysoka skola umeleckoprumyslova v Praze |

| Activity No. | C3 |
| --- | --- |
| Field | HE |

| Activity Type | SP-HE-SHORT |
| --- | --- |
| Description of the activity | Train the Trainers C3 - Explorations in communication and activation of teaching tools The C3 event in Berlin was a testing ground for the newly developed teaching (IO2) approaches which will be iterated and integrated in the DECODING CERAMICS platform (IO3). The trainees took actively part in workshops to engage with ceramics in analogue, hybrid, and digital formats. The topics stretched from traditional (manual) fabrication techniques with a visit at the Berlin based Royal Porcelain Manufactur (KPM) and an exercise in deciphering ancient chemical recipes (NOVA) and a broader material understanding (UAL, UMPRUM) to digital shaping and fabrication techniques (UMPRUM, KHB). The practice-based workshops were embedded in a series of lectures to get an in-depth view into the partner’s specific research areas and teaching approaches. The trainees came from the partner schools and their backgrounds whereas workshop masters, researchers, and teachers. KHB as a host organisation organised the training and its logistics. Attendance: the training was attended by 2 trainees from UAL, 3 trainees from NOVA, 3 trainees from UMPRUM, 3 trainees from KHB and 1 trainee from KHiO. Day 1 - Tradition and Material The event started with a study visit at to KPM where participants got insights of the high-quality manual and semi-automated production of traditional tableware. The company, founded in 1763 is a perfect example for traditional craftsmanship in areas, such as porcelain production and surface decoration, which are all facing the challenge of passing on skills and knowledge the next generation. In the afternoon UAL gave a lecture ‘What on Earth is Clay?!’. Focussing on clay as Material, firing temperatures, ecological implications and local specifications and the teaching methods for 1st year students. This was followed by a stamping workshop in the KPM modelling studio. Day 2 - From historical to futuristic A tour through KHB’s workshops followed by two parallel sessions which were jointly organised by UMPRUM and KHB, with a focus on digital fabrication techniques (robotics, CNC milling machine) and hacking them for a novel way of working with ceramic materials. During the KHB session participants experience and test ways of integrating code in the design and production processes using a grasshopper script (plug-in for CAD software Rhino) and with the stamping of patterns on ceramic tiles. Starting with an individual hand drawing which was photographed and processed for the robotic arm to stamp patters with a chosen tool, with trainees reflecting on possibilities or hurdles in working with digital tools and hybrid formats. UMPRUM session focused on the production of CNC milled plaster moulds and possibilities for interchangeable parts with digitally designed surface patterns. The session was the practical exploration, which was complemented by a lecture, which gave the participants an in-depth view into a PhD exploration on recycling clay in large scale production. Team NOVA gave a lecture about research on historical glaze and colouring techniques with ancient recipes and the challenge of translating and transferring this knowledge into contemporary restauration practices. Based on the lecture participants explored an old recipe ‘How to Make Green’ themselves and the chemistry behind certain colour making processes for surface decoration, with results explored and discussed on the next day. Day 3 – Augmented/Virtual Reality (AI/VR) and Student-led Courses This day was dedicated to KHiO’s teaching methods and formats. A lecture followed by two parallel sessions (A+B). A) focused on the use of simple 3D scanning techniques (photogrammetry) as a tool to explore scaling within the process of ceramics production. Working on large scale sculptures in ceramics education is challenging due to time capacities and material costs for students. KHiO illustrated how AI/VR tools help in a hands-on approach to explore small scale models in various dimensions and connect t to the analogue working process in ceramics. B) ’Collaborative Drawing on Clay ‘focused on the principle of self-taught student-led courses and participants could discuss advantages in giving students the freedom of defining their research and learning interests within a given framework pedagogy Ref Troublesome Knowledge? KHiO also gave a lecture on the Grid method for ceramic glazing recipes. The method will be explored and tested at the different partner schools, and it will be documented on the DECODING CERAMICS (IO3) platform. Learning Outcome: The participants earned extensive experience in working with analogue, digital and hybrid teaching formats to link both worlds. All lectures were video recorded. Selected outcomes were edited and integrated in IO3 DECODING CERAMICS platform. Activities were documented for social media posts and communication purposes. |
| Country of Venue | Germany |
| No. of Participants | 12 |
| Participants with Special Needs (out of total number of Participants) | 0 |
| Accompanying Persons (out of total number of Participants) | 0 |
| Is this a long-term activity? | No |
| Funded Duration (days) | 27 |
| Participating Organisations | Vysoka skola umeleckoprumyslova v Praze, KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG, UNIVERSIDADE NOVA DE LISBOA, THE UNIVERSITY OF THE ARTS LONDON, KUNSTHOGSKOLEN I OSLO KHIO |

## Participants in Learning/Teaching/Training Activities

### Participants' Profile

For each activity, please describe the background and profile of the participants involved in the learning, teaching or training activities. How were the participants selected, prepared and supported? If relevant, please describe any practical arrangement set for the participants, including training, teaching or learning agreements.

The CRAFT project delivered 3 short-term joint training workshops. Selection: each partner selected up to 3 trainers/practitioners taking part in the training and professional development training based on the following criteria:

- pursue research in one of the areas the project covers;

- exhibit a strong intellectual curiosity,

- willing to broaden their knowledge in a multidisciplinary manner through innovative learning approaches, and

- gender balance.

Staff exchanged during the short-term learning mobilities were provided with contact person at both the sending and receiving institution.

Preparation: before the short-term mobility, each partner organised pre-departure briefings for their staff involved. The briefings covered a range of practical matters concerning short mobility and will provide background information about the CRAFT project to maximise the learning experience. In terms of project specific preparation, each HEI share in advance with their participating trainers a briefing document with an agenda and practical information.

Health & safety: all staff and experts visiting the UAL’s premises were given a welcome induction tour of the building and facilities. Risk assessments were carried out for any activities where health and safety risks are envisaged prior to their delivery - however, the project did not carry out any high-risk activities.

After completing the training workshops, each participant received an electronic certificate of attendance.

### Participants' Recognition

Did your project make use of European instruments like Europass, ECVET, Youthpass, ECTS etc. or any national instruments/certificates for recognition or validation of the learning outcomes of the participants in the learning, teaching or training activities?

Yes

Please indicate the recognition/validation instruments used in your project: (Multiple selection possible)

Europass Curriculum Vitae (CV)

If you have used other recognition/validation instruments, please describe them:

### Intensive Study Programmes - Invited teachers

This section doesn't apply for this project

# Follow-up

## Impact

What was the project's impact on the participants, participating organisations, target groups and other relevant stakeholders?

The CRAFT strategic partnership triggered the following impacts:

Impact on ceramics as a discipline:

- established a new international network of ceramic educators and an open knowledge exchange platform for the development of new pedagogies and approaches to make subject more transdisciplinary and sustainable.

- facilitated an increased capacity for experimentation and prototyping within principles of heritage and future manufacturing.

- impacted on teachers/trainers/practitioners by providing the context and opportunity to develop new transformative pedagogies, building and participating in transdisciplinary projects with like-minded departments for the fostering of a shared community of practice based on open knowledge exchange, teaching methodologies and curricula.

- The ceramics education community by providing access to an open education platform (IO3), with interactive map of skills and expertise (IO1); and pedagogical approaches and teaching methods through decoding cards (IO2).

Systemic Impact: CRAFT established new forms of experiential pedagogy (IO2) through shared curricula and the development of transnational and cross-disciplinary modules open to all partnership members. CRAFT has instigated an expansion of Teacher/Trainer knowledge (IO3) through shared teaching repertoires. The partnership has increased interest in studying Ceramics across Europe, as evidenced at UAL where applications have increased by 100% in 2022 and 60% in 2023.

Impact on the partners: CRAFT benefited the partners by opening trans-disciplinary research, opportunities; increasing awareness and curiosity for faculty and student exchange; reinforcing teaching quality and excellence; and further placing the partners as holders of intangible cultural heritage in the role of subject custodians for the preservation of specialist and endangered knowledge.

CRAFT has benefitted the partners by:

UAL:

- enhanced UAL’s awareness of the discipline established new opportunities for educational collaboration and to highlight the need for preservation of knowledge and a call to action for educators.

- UAL has increased recognition with international organisations such the Crafts Council (U.K), NCECA (U.S.A), The Indian Ceramics Triennial and the BCB.

- the adoption of video demonstrations and annotation to share ceramic knowledge and to make tacit knowledge accessible and more understandable, will have significant impact across the CRAFT network and beyond into the wider discipline of ceramics and its associated pedagogies.

KHiO:

- focusing on the expert knowledge situated at ceramic knowledge institutions has strengthened KHiOs ceramic network and profile, nationally and internationally.

- integrating the Decoding Ceramics platforms and its learning resources into the existing study programme has already taken place, enriching the pedagogies of the programme.

- participating in a shared community like CRAFT has given an insight into the extensive network of ceramic knowledge across Europe and the importance of sharing this.

KHB:

- the inclusion of all KHB's staff, teachers, tutors, researchers, and workshop leaders - linked to the interdisciplinary ceramic pedagogy that is practised at KHB (practical work with ceramics, research-related work around ceramic, ceramic, and digital technologies).

- the inclusion of regional partners, alumni and manufacturers has also been a valuable building block for open knowledge transfer and extending the network of ceramic knowledge.

- permanently impacting on teaching and expanding the pedagogical repertoire at KHB. Since the ceramics workshop is an interface between all the university's departments, the impact of the project will directly or indirectly affect the whole school.

UMPRUM:

- involvement in the project had a direct impact on the restructuring of teaching as UMPRUM has adopted some of the teaching methods from partner institutions that complement the regular teaching and help level the knowledge of ceramics technology among students who do not have experience from specialised ceramic secondary schools.

- promoted the increased use of digital technologies, CAD/CAM and Robotics, as a regular medium for teaching and learning pedagogies.

NOVA:

- provided a significant opportunity to deepen the reflection on ceramic education and the use of technologies for

better preservation and education of skills. This resulted in applying mature digital tools for the specific goal of ceramics education and documentation of skills and processes.

- established a network of European collaborations, that have an impact on the staff directly involved, and the interdisciplinary work of the Nova Team, but also others that were in contact with the project, both from NOVA and School of Fine Arts, University of Lisbon.

- helped to introduce new technologies at NOVA to be used to produce ceramic objects, such 3D printing. The use of the pedagogical cards plays a fundamental role on this implementation.

What was the impact of the project at the local, regional, European and/or international levels? Please provide qualitative and quantitative indicators.

Impact at local and regional level, the CRAFT project involves key players from five regions that represent a spread of performance level according to the European Regional Innovation Scoreboard, combining areas considered to be Innovation Leader (UAL), Innovation Leader (KHiO & KHB) and Strong Innovator (NOVA and UMPRUM) and for which innovation and skill development in the area manufacturing design represents a timely and relevant contribution to their regional Smart Specialisation and present and future sustainable competitiveness.

The provision of skill sets and capabilities is expected to nurture leading regional ceramic manufacturing clusters. The academic partners are expected to consolidate our position as reference sectoral competence centers and hubs catalysing the regional economy and the ceramic manufacturing ecosystem. The implementation of the new teaching materials is going to impact on the wider ceramic industries by leading innovative experimentation and prototype creation contributing to industry growth and employability of designers.

UAL has extended its knowledge exchange network beyond its existing local ecosystem connecting with Craft Potters Association, The Kiln Rooms, and Manifold Studio into further regions with British Ceramics Biennial, the Leach Pottery, Burleigh Pottery and Steelite International and beyond to international collaborative opportunities with Veuva Lamego (PT), Odd Standard (NO) and Faiencerie Georges (FR) and the Associate Partner Royal Delft group (NL).

KHiO has established the connection and interest for the project amongst the external ceramic organizations and ceramic artists, through KHiOs network KHiO has also made connections with the Craft-Hub project (Creative Europe) led by Prof Berg (Oslo Metropolitan University). KHIO organized a joint clustering meeting held during transnational meeting TM5 to scope potential synergies and future cooperation.

UMPRUM has established new connections with IO1 mapping partners and strengthened relations with UMPRUM graduates and industrial partners on a regional level. Collaboration on IO2 between KHB and UMPRUM has been deepened: one of UMPRUM’s post-graduate students visited KHB for a workshop, where he presented to students. Increased cooperation between the Museum of Applied Arts in Prague and the Moravian Gallery in Brno. NOVA has established a collaboration with Oficinas do Convento to present their set of skills in videos of wood fire furnaces constructions with traditional techniques. The IO2 objectives and plans has brought the Faculty of Fine Arts of the University of Lisbon to discuss the implementation of new strategies for teaching ceramics to Portuguese art students, mainly when their experience level is extensive.

KHB has been reaching out to various regional actors from the ceramics industry and the creatives working in the fields. Students gained valuable insights into the diversity of the area and the state-of-the-art of the regional ceramics industry, laying the foundation for future potential collaborations. Companies, design practitioners, and museums (among others) have been visited in the region. Designer practices: Claudia Schömig Porzellan, Studio Cuzé, Yellow Nose Studio, Studio Anna Badur; manufacturers: Stefanie Hering Porzellan companies: Golem Kunst und Baukeramik, Königliche Porzellanmanufaktur, Hedwig Bollhagen; museums: Ofenmuseum Velten, Bröhan-Museum Berlin.

The project results are a relevant contributing to furthering the achieve the policy goal set out in the Communication - ‘Modernization of Higher Education - Supporting growth and jobs – an agenda for the modernisation of Europe's higher education systems SEC (2011)’ by improving of the quality and relevance of ceramic teaching methods to provide the graduates and researchers Europe sector needs. The impact in the short to medium term is to integrate the new jointly developed methodology and resources into the educational courses that cover the demand of the international labour market, with the formation of new professional skills at the intersection of heritage, creativity, and innovation.

Qualitative impact indicators include:

- 38 teachers/trainers/practitioners trained through short-term join training workshop delivered (C1-C3)

- The project has been presented at ECers 23rd 2-6 July 2023 (Lyon, FR), during the artistic research week at KHiO, 25th January 2022 where project was presented to research colleagues and students, together with demonstration using professional and educational content available on the Decoding Ceramics platform (IO3).

- Seminars where the project has been presented, such as Doctoral Program in Conservation and Restoration annual seminars (academic year 2020/2021). Design Transforms 21/22 during Duncan Hooson’s presentation. KHB department presentation at Salone del Mobile, Milan, on the platform of Salone Satellite, June 2022.

How did the project contribute to the achievement of the most relevant priorities as indicated in the description section?

The project contributed to achieving the following Erasmus+ Programme priorities:

- Social and educational value of European cultural heritage.

Partners joined forces to create a wide variety of knowledge and open exchange formats within the ceramic educations of each art school. This has played an essential role in achieving the goal of fostering excellence in teaching and skills development. It allowed bringing the most profound knowledge and expertise into each school's curriculum from various places and enriched ceramic education during the project duration and beyond. Solid ceramic knowledge has been combined with industry 4.0 technologies in experimental hybrid formats, and topics centred around current challenges like ecological aspects of ceramics, or the ever-changing professional landscape could be addressed.

- Supporting individuals in acquiring & developing basic skills and key competences.

The project has helped the partners with remote teaching, especially with first-year students who could not attend workshops. Also, the project has allowed joining forces among partners and other institutions identified in the mapping exercise to create a broader perspective of knowledge and skills and exchange formats within the ceramic educations in different contexts (not only "formal" schools). Finally, the partnership has started creating new teaching methods and tools, like step-by-step teaching modules, video demonstrations and lessons.

- Promoting and rewarding excellence in teaching and skills development,

Craft has promoted teaching excellence through shared curricula and projects across the partnership. The sharing of teaching has enabled the development of teaching practice across the partnership and a sense of collaborative skills development. In time, we expect this to reward teaching excellence by adopting a coherent shared teaching resources across Europe and recognition of excellence through an invitation to teach in institutions beyond the partnership or through Conference and Symposia.

## Dissemination and Use of Project Results

To whom did you disseminate the project results inside and outside your partnership? Please define in particular your targeted audience(s) at local/regional/national/EU level/international and explain your choices.

The partners, coordinated by UAL, created, and maintained a Communication and Dissemination Plan to plan and record the dissemination activities both implemented at local, regional, national and EU level to diffuse the pedagogy for ceramic education. The plan outlines:

- The strategy to communicate, disseminate, promote projects’ activities through awareness-raising, spreading information towards a wider public and all the relevant stakeholders.

- Key messages to sensitize and increase awareness on all relevant actors involved;

- The channels and audiences targeted (website, social media, press releases etc.); and

- A visibility package to promote and disseminate the project activities and outcomes.

Target audiences were identified and engaged were:

- Primary audience: University Academics, trainers, researchers, and practitioners in ceramics.

- Secondary audience: ceramic manufacturers, craftspeople and makers, museum conservators, technology providers.

The project targeted these different organisations at the:

- Institutional level: The target group within each HEI includes Teaching & Learning, Quality Assurance, Knowledge Exchange, and International Relation Offices.

- National Level: UK Crafts Council, Pôle Européen de la Céramique, British Ceramics Biennial, Norwegian Crafts, Deutsche Keramische Gesellschaft and Passa o Futuro and the Portuguese industrial association of ceramics.

- EU level: ISCAE, European Ceramic Society, ELIA, EKWC, ECerS and ENoLL European Living Lab Networks.

- International: International Association of Ceramics, ICOM, CUMULUS, NCECA, Indian Ceramics Triennial, Jingdezhen Ceramics Biennial.

The active involvement of the partners and of the dissemination through the networks to which they belong supported the promotion and dissemination of project’s results and will allow a follow up in view of future development and enlargement both partnership and the activities. The partners during the project implemented the following Communication and Dissemination activities:

- UAL focused dissemination activities by targeting the academic community design students, staff, researchers. Results were disseminated by UAL and NOVA at conferences like ECerS 2023 - the Exhibition of the European Ceramic Society and briefed and UAL advocated support for curriculum innovation from educational stakeholders such as the Craft Potters Charitable Trusts, the Arts & Humanities Research Council (U.K.) and the Indian Ceramics Triennial. The coordinator also presented the project and its results to Professor Christopher Smith, Executive Chair of the UK Arts and Humanities Research Council (AHRC) during his visit at UAL on 4th May 2023. UAL curated the delivery of final multiplier event Decoding Ceramics on 15 June 2023 in London.

- NOVA presented the project during the annual European Research Night at VICARTE’s that attracted more than 200 people of all age and organised seminars for 12 PhD students of the Doctoral Programme in Conservation and Restoration, 2022 and 2023 as well as two seminars for the students of the Master in Glass and Ceramics Art and Science for the academic years 2022 and 2023. NOVA featured the project in KERAMICA, a specialist magazine curated by the Portuguese industrial association of ceramics.

- KHB disseminated the project’s results via the university's website and social media and at Open Days of weißensee school of art and design berlin in July 2021, 2022, and 2023. The project results expand the pedagogical repertoire at KHB. Since the ceramics workshop is an interface between all the university's departments, the impact of the project will directly or indirectly affect the whole school, extending to other schools and the ceramics community in Germany.

- KHiO spread awareness and encourage a dialogue around research-based teaching strategies amongst both the academic community, as well a ceramic practitioner in Norway as well as abroad through the university's digital website, social media channels and at events open to the public such as the Research Week.

- UMPRUM promoted the project through its wide network of specialised art high schools, craft societies, industrial companies, and museums e.g., the Museum of Applied Art. Presentation and workshop were given at Secondary School of Applied Arts Uherské Hradiště on 6th May 2022 and on 11th-12th May 2023.

What kind of dissemination activities did your partnership carry out and through which channels? Please also provide information on the feedback received.

Dissemination was implemented according to phases, from an initial communication approach through to intensive knowledge exchange and reciprocal learning within an expanding ecosystem. A Dissemination and Communication Plan was prepared in M3 and periodically updated to define strategy and tools for sharing information and engaging key stakeholders.

The communication tools and channels were used:

- Common visual identity created, including logo, and templates. UAL developed these resources to give the project a common external image to communicate clearly and consistently.

- A project website (https://craft.arts.ac.uk/) designed and managed by UAL as well as webpages dedicated to the project on the institutional websites of the partners providing information on the project and its activities (e.g. https://www.arts.ac.uk/research/current-research-and-projects/craft)

- Social media channels like Facebook, Twitter and Instagram for image-based communication were used by the partners.

- Media relations and coverage: UAL and KHIO created press releases to announce the project, which were disseminated leveraging on the partners’ networks https://issuu.com/apicer-ceramicsportugal/docs/keramica369. The project received extensive coverage in the magazine of the Portuguese industrial association of ceramics KERAMICA and in the newsletters of the Norwegian Craft Association and of Norwegian Crafts. An interview with the magazine Forskerforum is also planned, which will be published in November.

- Multiplier Event (E1) - “Decoding Ceramics’: UAL organised the delivery of the ‘CRAFT: Decoding Ceramics’ event to disseminate the project results: targeted the artistic ceramic community and hold during the Central Saint Martins Degree Show which gathered leading experts and practitioners and involved 52+ attendees.

- Stakeholders' briefings through presentations and meetings where the project results were presented and demonstrated (e.g., presentation to Executive Chair of the Arts Humanities Research Council, discussing follow on funding opportunities and a mmeeting with Senior Faculty Nanjing Academy of Fine Arts, including Ms Sabrina Long - Dean, Art and Design and Principle School of Young Talents, Dr Jeffery Tan – Dean at the Centre of Lifelong Learning and Mr Fadzli Jamil Vice Dean, 3D Design Programme – presenting IO1 mapping process, IO2 pedagogical approaches and discussing how to engage NAFA in network going forward.

- Presentations and talks at international conferences such as:

- Milan Design Week 7th-12th June 2022 Salone del Mobile, Salone Satellite – KHB presented results of the semester project "CRAFT – Colours and Topographies” in which new teaching methods were tested (e. g. the CNC milling of plaster moulds and a workshop format for ceramic 3D-print with natural clays)

- National Council on Education for the Ceramic Arts (NCECA) Conference, 15th-18th March 2023, Cincinati (USA) the Co-ordinator presented IO1 + IO2 to the Board, including director Josh Green, and members Steve Hilton, Shoji Satake and shared plans for platform.

- Prototype Sprint at Křehký Mikulov" 26th-28th May 2023; exhibition of assignment outcomes which utilised pedagogical approaches, (Troublesome Knowledge) introduced by UAL in Prague during Transnational Meeting 4;

- ECerS 2023 - Exhibition of the European Ceramic Society - 2-6 July 2023 in Lyon (FR) where a presentation of a

joint paper ‘Decoding Ceramics – the digital transmission of knowledge in intangible cultural heritage’ (UAL; NOVA).

- Faculty seminars and peer learning activities were delivered to foster knowledge exchange and circulation of best practices across the teaching community.

- Clustering activities and cooperation with other projects and sectorial association such as the:

- H2020 T-Factor by extending the teaching of ceramic skills in meanwhile spaces at Trafaria in Lisbon and Somerstown Community association in London.

- CraftHUB project – KHIO organised a clustering meeting to stimulate cooperation during the Transnational Meeting (TM5) in Oslo, with Arild Berg. NOVA is also a partner of the project contributing to the conservation science aspect of the research.

- KHiO registered the project in Cristin - Norwegian Agency for Shared Services in Education and Research, and in KHiODA - Oslo National Academy of the Arts Digital research archive.

  - Public engagement and outreach activities: UMPRUM, KHB and NOVA presented the project at public engagement events such as workshop for high schools for 20 attendees in September 2021, annual days of open doors in July 2022 and 2023 at KHB for 2000 attendees, and workshop for high schools for 20 attendees in December 2021 at NOVA. KHiO presented the project to an audience of 50 attendees at a public event during Research Week 2022 in Oslo.

Erasmus+ promotes an open access requirement for all materials produced through its projects. In case your project has produced intellectual outputs/tangible deliverables, please describe if and how you have promoted free access to them by the public. In case a limitation was imposed for the use of the open licence, please specify the reasons, extent and nature of this limitation.

The CRAFT partnership released the intellectual outputs and any dissemination material under Creative Common License Share Alike 4.0. Attribution-Non-Commercial (CC BY-NC) to make them available to the public as open educational resources (OERs) via the Decoding Ceramics platform (IO3), the partners’ websites and their institutional platforms and repositories, and through the E+ Project Results Platform. Course material, edited lectures and other content harvested from the teaching and learning activities were collated, re-formatted and presented to allow future engagement with this material by a European-wide design HEI community.

The release of the outputs as Open Educational Resources is expected to boost content use and reuse. Learning resources will also be shared in other open educational content repositories and in formats suitable to guarantee interoperability with state-of-the-art open learning management systems. The project produced content using standard interoperable multimedia formats like DOC, TXT, PDF, HTML (for text); PNG, JPG, PDF, TIFF (for images); WAV and MP3 (for audio); AVI, MP4, MPG (for video) and STL and OBJ (for 3D formats). These formats are commonly used and support enabling interoperability and portability of content.

How have you ensured that the project's results will remain available and be used by others?

All partners have committed to long-term sustainability and continuation based on the principles of open-access and innovation to results and outputs. The intellectual outputs delivered are expected to inform the sectoral practice through the adoption of innovative teaching and learning resources and approaches. These resources will continue to be hosted and be freely available and accessible, even after the end of the project through the Decoding Ceramics Platform. Project partners have committed to the hosting, upkeep and curation of the Platform for 5 years beyond the project end date, with resources committed for hosting fees. There is a plan to onboard other institutions in the next 6 months to distribute responsibility for management beyond the original partnership. The platform is expected to continue to grow, with partners managing and curating user generated content.

Mapping effort will continue beyond the life of the project, as IO1 built an approach and process for mapping the discipline, giving partners the tools and capacity to continue with this task. It will also provide a call to action across Europe for others to participate and contribute to continued mapping. The online interactive map (IO1) provides a directory of craftspeople, production centres, residency and research, heritage and conservation practices, and educational practices, which will continue to be available aggregating additional content beyond this project.

IO2 teaching cards, re-titled ‘Decoding Cards’, gather several pedagogic methods tested by the partners within the project are documented in detail in the form of image and film material as well as descriptive and reflective texts. Partners will continue to contribute to the library of pedagogical practices on a rolling basis, with new projects recorded and inputted to the database and held for the public on the Platform.

The collected materials are embedded and made freely accessible through the Decoding Ceramics digital platform (IO3) - a one stop shop repository to provide access to the intellectual outputs (IO1-IO2). The platform will continue to grow after the end of the project and will be filled with case studies and resources. New methods will be developed continuously to draw students' attention to the potential of ceramic materials and production methods, to make traditional and new tools accessible to them and to open relevant topics. In this way, Europe-wide inter-university cooperation can be supported, and ceramic knowledge can be maintained and constantly expanded, even beyond

classical ceramic education. The Decoding Ceramic platform provides access to a coherent body of high-quality teaching resources available to teachers, trainers, students This also comprises a dynamic and an interactive map of European skills and knowledge (IO1); pedagogical tools, including creative challenges and skill-based projects and teaching methods; a collection of interviews, video demonstrations, step-by-step tools and diagrams, drawings, and process illustrations (IO2). The platform (IO3) as an aggregator of teaching and learning resources will continue to be used after the end of the project hosting all the dissemination material and the outputs. It is expected that it will become a reference resource for the wider HE ceramic community.

As a result of the communication and dissemination activities, we expect that the proposed teaching and learning approaches and resources will be also absorbed and implemented in the educational program of each partner so results will be used and augmented with new contributions to maximise the impact and ensure the academic level of the resources developed.

How did you see the potential to use this project's approach in other projects on a larger scale and/or in a different field or area?

The CRAFT strategic partnership established a cross-European network of HEI’s acting as subject custodians for the ceramic discipline. We expect to open the network to more institutions after the funded project ends 10+ additional organisations are expected to get involved within 5 years from the project end.

The methodology for capturing disappearing skills or intangible knowledge is directly transferable across all crafts sectors where there is a consortium of HEI’s to act as the subject custodian and an adjacent network of artists, small studios, manufacturers, museums, and research centers.

The intellectual outputs lend themselves to other disciplines within the craft sector.

- IO1: Mapping craft places, skills, processes, technologies, intangible knowledge and training practices for making ceramics.

- IO2: Developing pedagogical approaches and innovative teaching methods to teach crafts to sustain the future of the subject.

- IO3: Developing skills and resources, offering repertoires of knowledge and practice for making crafts.

Other Craft sectors include Glass, Metals, Jewellery, Woodwork and Textiles.

COVID-19 forced some improvisations that have resulted in some unexpected innovations that have exciting potential to be transformative across the craft pedagogy sector.

- Annotated video demonstrations that look at making gestures and tacit knowledge explicit to the learners will transform access to specialist craft knowledge.

- The Pedagogy and curriculum mapping tool (platform) encourages the sharing of best practices between partners and establishes points of intersection for collaborative teaching approaches pointing to a new distributed open-access form of education.

- The interactive map enables the viewer to dig deep into the map linking via skills, region, materiality etc.

To test the transferability potential of the results developed by the CRAFT project, the partners jointly designed ‘CRAFT LABS 5.0 Technologies for human-centric innovation’ a bid submitted in response to the call topic

‘HORIZON-CL2-2022-HERITAGE-01-04 Traditional crafts for the future: a new approach’. The ambition was to create a digitally enhanced craft methodology and pedagogy, and a curriculum with three pathways (ceramics, glass, and porcelains) combining traditional craft skills with innovative technologies and business/entrepreneurship skills. The bid has not been retained for funding.

## Sustainability

What are the activities and results that will be maintained after the end of the EU funding, and how will you ensure the resources needed to sustain them?

A successful cooperation between partners will lead to further collaborative research on craft futures. After the project, partners have committed to work on the following exploitable results to ensure the sustainability of the project aims:

1) To stimulate the adoption, use of the tools, content and teaching methods developed by the project. The Teaching cards (IO2) and the Decoding Platform (IO3) will be embedded in the training and pedagogy practices of partners and widen the range of the learning resources offered at BA, MA, and PhD levels. Partners will share these approaches

with academics, professionals and makers through conferences, symposia and lectures to train peers.

- Enriching and aggregating the interactive map (IO1) with additional points of interest with user-generated content provided by the community. In the short term, participation in the platform will be encouraged through a

community-based and open-science business model aimed at aggregating more points of interest and knowledge resources for the map. Partners will review submissions through a triannual curation meeting. In due course the curation team will be opened to new participants from the wider network. The development of a prosumer network of contributors will be fostered and supported.

- Aggregating on the Decoding Ceramics platform new user-generated content in the form of teaching cards and tutorials provided by the platform users. In the long term, as the platform and network grow participation in the platform will be driven by user generated content in the form of video demonstrations, instructables and step by steps, reviewed by a curatorial team, with support offered to contributors where needed.

- Enlarging and Strengthening the Decoding Ceramics Network internationally involving more HEIs and ceramics trainers and researchers from diverse background and locations, in ceramics teaching and related fields to exchange of good practices and the adoption of the proposed methods in their curricula.

To encourage project sustainability in the short-term the following dissemination and exploitation activities were carried out after completion to foster the promotion and use of the project results and to attract more stakeholders.

  - KHB presented the project’s outcome at the Grassimesse craft fair at Grassimuseum Leipzig in October 2023 (ca. 10000 visitors) and plans a presentation at Zeughausmesse Berlin in November 2023.

  - UMPRUM will be exhibiting the results of testing the Storytelling teaching strategy (IO2) at the Moravian gallery in Brno from 17th November 2023 to 31st August 2024 as a part of Made by fire exhibition. On 6th November 2022 UMPRUM presented the project to visitors from MOME (Budapest, Hungary) Katalin Cecília Hutter (programme manager) and Zoltán Lublóy.

  - UAL with the support of the Associate Partner, the British Ceramics Biennial (BCB) delivered a Decoding Ceramics symposium on 11th October 2023 at the Potteries Museum in Stoke on Trent. The event promoted the project results, attracting 100+ educators, students, and craftspeople, from institutions across the UK, Manchester School of Art, Cardiff Met, University of Ulster, Staffordshire University, Royal College of Art, Carmarthen school of art and other

non-academic organizations such as the Clay College Stoke On Trent, the International Ceramics Festival (Wales), Keramiekmuseum Princessehof (NL). On 14th December 23, UAL will present the CRAFT Project at ‘Crossover and Coordination’ Art & Industry cooperation conference at the Jingdezhen International Ceramics Biennial in China and at the International Ceramic Education Alliance on 15th December 23.

Potential long-term sustainability:

The partnership has developed a sustainability plan beyond the project lifetime, supported by existing strategic and institutional resources. The plan is to enlarge the partnership, develop and nurture a distributed community of practice and run a certified professional development programme and academy for ceramic educators, teachers, and trainers. The extrapolated sustainability model will enable the continued offering of training opportunities fully structured and integrated into curricula. The cooperation model will bring visibility to the project and stakeholders, key actors and end-users involved across Europe. The sustainability planning will go through a series of iterations:

  - At consortium level ensuring that all HEIs will institutionalise the methodological approaches and will continue to use and expand the training resources and teaching methods.

  - Externally through attracting and engaging third parties in the use and provision of new learning resources and integrating new disciplinary contributions.

To build on and to further develop the result developed by the E+ KA2 CRAFT project, the partners are considering applying for the Horizon-MSCA-SE-2023-1-1 MSCA Staff Exchange call to strengthen and enlarge further the network

- Budget

this section gives a detailed overview of the final amount of the EU grant you request;

  - Budget Summary

| OID of the Organisation | Name of the Organisation | Country of the Organisation | Project Management and Implementation | Transnational Project Meetings | Intellectual Outputs | Multiplier Events | Learning/Teaching/Training Activities |  |  |  | Special Needs Support | Exceptional Costs | Exceptional Cost Guarantee | Total (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Travel | Individual Support | Linguistic Support | Exceptional Costs for Expensive Travel |  |  |  |  |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 18,000.00 | 7,475.00 | 71,690.00 | 5,600.00 | 1,375.00 | 1,590.00 | 0.00 | 0.00 | 0.00 | 1,777.59 | 0.00 | 107,507.59 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 9,000.00 | 3,450.00 | 55,430.00 | 0.00 | 1,100.00 | 1,272.00 | 0.00 | 0.00 | 0.00 | 3,033.98 | 0.00 | 73,285.98 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 9,000.00 | 5,935.00 | 61,632.00 | 0.00 | 1,365.00 | 1,908.00 | 0.00 | 0.00 | 0.00 | 2,052.02 | 0.00 | 81,892.02 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 9,000.00 | 7,845.00 | 41,648.00 | 0.00 | 1,090.00 | 1,590.00 | 0.00 | 0.00 | 0.00 | 720.56 | 0.00 | 61,893.56 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 9,000.00 | 9,715.00 | 49,868.00 | 0.00 | 2,985.00 | 2,862.00 | 0.00 | 0.00 | 0.00 | 1,506.35 | 0.00 | 75,936.35 |
| Total |  |  | 54,000.00 | 34,420.00 | 280,268.00 | 5,600.00 | 7,915.00 | 9,222.00 | 0.00 | 0.00 | 0.00 | 9,090.50 | 0.00 | 400,515.50 |

7.1.1. Project Total Amount

400,515.50

Project Total Amount Reported (Calculated)

Please provide any further comments you may have concerning the above figure.

  - Project management and implementation

| OID of the Organisation | Role of the Organisation | Name of the Organisation | Country of the Organisation | Total |
| --- | --- | --- | --- | --- |
| E10107200 | Partner | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 9,000.00 |
| E10153935 | Partner | UNIVERSIDADE NOVA DE LISBOA | Portugal | 9,000.00 |
| E10203634 | Beneficiary | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 18,000.00 |
| E10103845 | Partner | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 9,000.00 |
| E10105490 | Partner | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 9,000.00 |
| Total |  |  |  | 54,000.00 |

  - Transnational Project Meetings

| OID of the Sending Organisation | Name of the Organisation | Country of the Organisation | Total No. of Meetings | Total Number of Participants in All Meetings | Distance Band | Grant per participant | Total (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 2 | 0 - 99 km | 0.00 | 0.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 3 | 0 - 99 km | 0.00 | 0.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 1 | 100 - 1999 km | 575.00 | 575.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 2 | 0 - 99 km | 0.00 | 0.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | 1 | 1 | 100 - 1999 km | 575.00 | 575.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 4 | 0 - 99 km | 0.00 | 0.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 4 | 100 - 1999 km | 575.00 | 2,300.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 1 | 0 - 99 km | 0.00 | 0.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 1 | >= 2000 km | 760.00 | 760.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1 | 1 | 100 - 1999 km | 575.00 | 575.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 3 | 0 - 99 km | 0.00 | 0.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 2 | >= 2000 km | 760.00 | 1,520.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1 | 2 | 0 - 99 km | 0.00 | 0.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 3 | >= 2000 km | 760.00 | 2,280.00 |

| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 3 | >= 2000 km | 760.00 | 2,280.00 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 4 | 0 - 99 km | 0.00 | 0.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 2 | 100 - 1999 km | 575.00 | 1,150.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 4 | 0 - 99 km | 0.00 | 0.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1 | 3 | >= 2000 km | 760.00 | 2,280.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 5 | 0 - 99 km | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 4 | 0 - 99 km | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 5 | 0 - 99 km | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 4 | 100 - 1999 km | 575.00 | 2,300.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | 1 | 3 | 100 - 1999 km | 575.00 | 1,725.00 |
| Total |  |  |  |  |  |  | 34,420.00 |

  - Intellectual Outputs

| OID of the Organisation | Name of the Organisation | Country of the Organisation | Output Identification | Category of Staff | No. Of Working Days | Grant per Day | Total (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | O1 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 44 | 241.00 | 10,604.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | O2 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 70 | 214.00 | 14,980.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | O3 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 91 | 241.00 | 21,931.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | O3 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 165 | 214.00 | 35,310.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | O1 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 100 | 214.00 | 21,400.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | O2 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 91 | 137.00 | 12,467.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
|  |  |  |  | Managers | 0 | 0.00 | 0.00 |

| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | O3 | Teachers/Trainers/Researchers/Youth Workers | 115 | 137.00 | 15,755.00 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | O2 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 129 | 214.00 | 27,606.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | O3 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 85 | 214.00 | 18,190.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | O3 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 85 | 137.00 | 11,645.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | O1 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 74 | 214.00 | 15,836.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | O1 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 128 | 137.00 | 17,536.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | O2 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 85 | 137.00 | 11,645.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | O1 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 164 | 137.00 | 22,468.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | O2 | Managers | 0 | 0.00 | 0.00 |
|  |  |  |  | Teachers/Trainers/Researchers/Youth Workers | 95 | 241.00 | 22,895.00 |
|  |  |  |  | Technicians | 0 | 0.00 | 0.00 |
|  |  |  |  | Administrative support staff | 0 | 0.00 | 0.00 |
| Total |  |  |  |  | 1521 |  | 280,268.00 |

  - Multiplier Events

| OID of the Organisation Organising the Event | Name of the Organisation | Country of the Organisation | Event Identification | Country of Venue | No. of Local Participants Physical Activities | Grant per local Participant Physical Activities | No. of Foreign Participants Physical Activities | Grant per Foreign Participant Physical Activities | No. of Participants in Virtual Activities | Grant per Participant in Virtual Activites | Total Amount (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | E1 | United Kingdom | 48 | 100.00 | 4 | 200.00 | 0 | 0.00 | 5,600.00 |

| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | E2 | Czech Republic | 0 | 100.00 | 0 | 200.00 | 0 | 0.00 | 0.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  | 48 | 200.00 | 4 | 400.00 | 0 | 0.00 | 5,600.00 |

  - Learning/Teaching/Training Activities

7.6.1. Travel

| OID of the Sending Organisation | Name of the Organisation | Country of the Organisation | Activity No. | Activity Type | Distance Band | Travel Grant per Participant | No. of Participants | Exceptional Costs for Expensive Travel | Total (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C1 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 1 | 0.00 | 275.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C2 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 2 | 0.00 | 550.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C3 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 1 | 0.00 | 275.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | C1 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 3 | 0.00 | 825.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | C2 | Short-term joint staff training events | 100 - 499 km | 180.00 | 3 | 0.00 | 540.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | C1 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 2 | 0.00 | 550.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | C3 | Short-term joint staff training events | 100 - 499 km | 180.00 | 3 | 0.00 | 540.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C1 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 3 | 0.00 | 825.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C2 | Short-term joint staff training events | 2000 - 2999 km | 360.00 | 3 | 0.00 | 1,080.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C3 | Short-term joint staff training events | 2000 - 2999 km | 360.00 | 3 | 0.00 | 1,080.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | C2 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 3 | 0.00 | 825.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | C3 | Short-term joint staff training events | 500 - 1999 km | 275.00 | 2 | 0.00 | 550.00 |
| Total |  |  |  |  |  |  | 29 | 0.00 | 7,915.00 |

7.6.2. Individual Support

7.6.2.1. Short-term Learning/Teaching/Training Activities

| OID of the Sending Organisation | Name of the Organisation | Country of the Organisation | Activity No. | Activity Type | Participants (Without Accompanying Persons) |  |  |  |  |  | Accompanying Persons |  |  |  |  |  | Total (Calculated) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Funded Duration (days) Physical Activity | Funded Duration (days) Virtual Activity | No. of Participants (without accompanying persons) | Grant per Participant Physical Activity | Grant per Participant Blended Activity | Grant per Participant Virtual Activity | Funded Duration (days) Physical Activity | Funded Duration (days) Virtual Activity | No. Of Accompanying Persons | Grant per Accompanying Person Physical Activity | Grant per Accompanying Person Blended Activity | Grant per Accompanying Person Virtual Activity |  |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C1 | Short-term joint staff training events | 3 | 0 | 1 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 318.00 |
| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C2 | Short-term joint staff training events | 3 | 0 | 2 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 636.00 |

| E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | C3 | Short-term joint staff training events | 3 | 0 | 1 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 318.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | C1 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | C2 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | C1 | Short-term joint staff training events | 3 | 0 | 2 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 636.00 |
| E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | C3 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C1 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C2 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | C3 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | C2 | Short-term joint staff training events | 3 | 0 | 3 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 954.00 |
| E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | C3 | Short-term joint staff training events | 3 | 0 | 2 | 318.00 | 0.00 | 0.00 | 0 | 0 | 0 | 0.00 | 0.00 | 0.00 | 636.00 |
| Total |  |  |  |  | 36.00 | 0 | 29 | Total |  |  | 0.00 | 0 | 0 | Total |  |  | 9,222.00 |

7.6.2.2. Long-term Learning/Teaching/Training Activities

This section doesn't apply for this project

7.6.4. Exceptional Costs for Expensive Travel

7.6.3. Linguistic Support

This section doesn't apply for this project

7.7. Special Needs Support

This section doesn't apply for this project

7.8. Exceptional Costs

This section doesn't apply for this project

| ID | OID of the Organisation | Name of the Organisation | Country of the Organisation | Description and Justification | Total Incurred Cost | Grant Requested (75%) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | E10203634 | THE UNIVERSITY OF THE ARTS LONDON | United Kingdom | Valetine Clay Lt invoice N. 49818 dated on 23/02/2022 to procure 12.5 kg special porcelain + LF white earthernware £1,446.27 (EUR/GBP exchange rate source ECB £1.160) equal to € 1,677.67 Bentley Advanced Materials Invoice N. 331795 dated on 25/03/2022 to procure Pottery Plaster 25 kg + delivery £596.78 (EUR/GBP exchange rate source ECB £1.160) equal to € 692.44 All invoices are inclusive of non-deductible VAT. | 2,370.12 | 1,777.59 |
| 2 | E10103845 | KUNSTHOGSKOLEN I OSLO KHIO | Norway | Clay for video production for IO2 and IO3 procured through 3 invoices from the supplier: 1) WALDM ELLEFSEN AS, Invoice number 170222, dated 20/10/2022, for 12,358 kr (EUR/kr rate source ECB 0.09614kr) equal to € 1,188.10 2) WALDM ELLEFSEN AS, Invoice number 170596, dated 11/11/2022, for 12,100 kr (EUR/kr rate source ECB 0.09696kr) equal to € 1,173.22 3) WALDM ELLEFSEN AS, Invoice number 169483, dated 31/08/2022, for 17,300 kr (EUR/kr rate source ECB 0.09734kr) equal € 1,683.98 All costs include non-deductible VAT. | 4,045.30 | 3,033.98 |
| 3 | E10105490 | KUNSTHOCHSCHULE BERLIN-WEISSENSEE HOCHSCHULE FUER GESTALTUNG | Germany | 1) Börkey Keratech Gmbh, Invoice Number 331, dated 01/02/2022 to procure different materials for IO2 experimental testing of new teaching methods total cost €185.56 2) Börkey Keratech Gmbh, Invoice Number 1425, dated 30/06/2022 to procure Glaze for IO2 experimental testing of new teaching methods (https://craft.di.fct.unl.pt/card/369) total cost €248.26 3) CASEA GmbH, Invoice Number 15152108, dated 31/05/2022 to procure Plaster for IO2 experimental testing of new teaching methods total cost €266.51 4) CASEA GmbH, Invoice Number 15165617, dated 17/01/2023 to procure Plaster for IO2 experimental testing of new teaching methods total cost €307.97 5) Börkey Keratech Gmbh, Invoice Number 230132, dated 10/01/2023 to procure Glaze for IO2 experimental testing of new teaching methods (https://craft.di.fct.unl.pt/card/369) total cost €148.23 6) Carl Jaeger Gmbh, Invoice Number 744978, dated 21/04/2022 to procure Glaze and kiln furniture for IO2 experimental testing of new teaching methods total cost €182.78 7) BSZ Keramikbedarf Gmbh, Invoice Number 22260703, dated 05/05/2022 to procure different materials and tools for IO2 exp. testing of new teaching methods total cost €73.28 8) CASEA GmbH, Invoice Number 1000023749, dated 28/04/2023 to procure plaster for IO2 experimental testing of new teaching methods total cost €350.81 9) CASEA GmbH, Invoice Number 1000024595, dated 24/05/2023 to procure plaster for IO2 experimental testing of new teaching methods + Packaging and shipping of plaster for IO2 experimental testing of new teaching methods total cost €490.04 10) Börkey Keratech Gmbh, Invoice Number 230750, dated 09/05/2023 to procure grogged stoneware clay for IO2 experimental testing of new teaching methods; porcelain casting clay for IO2 experimental testing of new teaching methods, total cost €754.85. All costs are inclusive of non-deducative VAT. | 2,736.02 | 2,052.02 |

| 4 | E10153935 | UNIVERSIDADE NOVA DE LISBOA | Portugal | 1) Barracha Fornos e Tecnologias Termodinamicas, Ldª, Invoice number B/3581, dated 07/11/2022 to procure crucibles and silica for the demonstrations of C2 and C3 and for the work developed to prepare educational cards for IO2 and IO3 total cost € 1009.46. 2) Laborspirit, Lda - Invoice number 1093, dated 19/01/2023 to procure chemical reagents for the demonstrations of C2 and C3 and for the work developed to prepare educational cards for IO2 and IO3 total cost € 999.00. All costs include non eligible VAT. | 2,008.46 | 1,506.35 |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | E10107200 | Vysoka skola umeleckoprumyslova v Praze | Czech Republic | 1) H+K Keramicke maerialy sro, Invoice Number 4323210, dated 12/04/2023 to procure clay for filming demos and workshops total costs 22500 CZK (EUR/CZK rate source ECB 0.0427 CZK) equal to € 960.75. Cost inclusive of non deductible VAT. | 960.75 | 720.56 |
| Total |  |  |  |  | 12,120.65 | 9,090.50 |

7.9. Exceptional costs - Guarantee

This section doesn't apply for this project

|  | DRAFT Report Form |
| --- | --- |
| Cooperation for innovation and the exchange of good practices: 2020 KA2 |  |

# Annexes

additional documents that are mandatory for the completion of the report;

Please note that all documents mentioned below need to be attached here before you submit your form online. Before submitting your report to the National Agency, please check that:

all necessary information on your project have been encoded in Mobility Tool+

The report form has been completed using one of the mandatory languages specified in the Grant Agreement.  you have annexed all the relevant documents:

the Declaration of Honour signed by the legal representative of the beneficiary organisation.  the necessary supporting documents as requested in the grant agreement.

You have saved or printed the copy of the completed form for yourself.

you have uploaded the relevant results on the Erasmus+ Project Results Platform:

## List of uploaded files

no uploaded files yet